## 42 a
Tabla 42 (a)
CUENCA DEL ARROYO MALDONADO -PROYECTO EJECUTIVO
Cronograma de Obras
Actividad | Año | 2005 |  |  |  | 2006 | [11 empty] | 2007 | [11 empty] | 2008 | [11 empty] | 2009 | [11 empty] | 2010 | [11 empty] | 2011
| mes | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| Total | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76
Provisión y puesta en obra de tunelera 1 | 12 | bar: 2005 9 1 to 2006 8 12
Montaje tunelera 1 | 2 | bar: 2006 9 13 to 2006 10 14
Ejecución de Túnel largo | 27 | bar: 2006 11 15 to 2009 1 41
Cámaras Túnel largo | 18 | bar: 2008 3 31 to 2009 8 48
Red secundaria tunel corto | 24 | bar: 2006 9 13 to 2008 8 36
Provisión y puesta en obra de tunelera 2 | 12 | bar: 2005 11 3 to 2006 10 14
Montaje tunelera 2 | 2 | bar: 2006 11 15 to 2006 12 16
Ejecución Túnel corto | 14 | bar: 2007 1 17 to 2008 2 30
Red secundaria tunel largo | 26 | bar: 2007 7 23 to 2009 8 48
Cámaras Túnel corto | 13 | bar: 2007 8 24 to 2008 8 36
Entabicado | 15 | bar: 2007 8 24 to 2008 10 38

## 42 b
PROYECTO EJECUTIVO CUENCA DEL ARROYO MALDONADO | [5 empty] | 0 | 0 | 0 | [66 empty] | TABLA 42B
|  | 0 |  |  |  | 0 | 0 | 0
TUNELES ALIVIADORES CONSTRUIDOS CON TUNELERA | [5 empty] | 0 | 0 | 0
|  | 0 |  |  |  | 0 | 0 | 0
RUBRO Nº | ITEM | 0 | DESCRIPCION |  | UNIDAD | 0 | 0 | 0 |  |  | DURACION (Meses) |  | PLAZO PARC | MES DE INICIO | AÑO 1 | [11 empty] | AÑO 2 | [11 empty] | AÑO 3 | [11 empty] | AÑO 4 | [11 empty] | AÑO 5 | [11 empty] | AÑO 6
|  | Contro P |  |  |  | CANTIDAD | COSTOS | 0 |  |  |  | PRECIO | MESES |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66
| 0 | 0 | 0 |  | 0 | 0 | UNITARIO | PARCIAL | TOTAL | %
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | AÑO 3 34: PUESTA EN FUNCIONAMIENTO DE TUNEL 1 (CORTO)
1 | 0 | 0 | Ingeniería de detalles | 100% | Gl | 1 | 2418600 | 2418600 | 2418600 | 1.056% | 11 | 3955851.2763 |  |  | AÑO 1 1: 20%; AÑO 1 2: 20%; AÑO 1 3: 20%; AÑO 1 4: 5%; AÑO 1 5: 5%; AÑO 1 10: 5%; AÑO 3 25: 5%; AÑO 3 26: 5%; AÑO 4 38: 5%; AÑO 5 50: 5%; AÑO 5 51: 5%
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | bar: AÑO 3 34
2 | 0 | 0 | Tareas Preliminares |  |  | 1 | 0 | 0 | 3582932.0996 | 1.565% | bar: AÑO 3 34
0 | 2.1 | 0 | Instalación del Obrador principal | 100% | Gl | 1 | 481025.9018 | 481025.9018 | 0 | 0 | 3 | 786763.8004 |  |  | AÑO 1 1: 20%; AÑO 1 2: 30%; AÑO 1 3: 50%
0 | 2.2 | 0 | Movilización y desmovilización equipos convencionales | 100% | Gl | 1 | 183463.36 | 183463.36 | 0 | 0 | 3 | 300071.846 |  |  | AÑO 1 1: 20%; AÑO 1 2: 30%; AÑO 1 3: 40%; AÑO 6 66: 10%
0 | 2.3 | 0 | Instalación de Fábrica de Dovelas | 100% | Gl | 1 | 1055242.1318 | 1055242.1318 | 0 | 0 | 7 | 1725949.2822 |  |  | AÑO 1 1: 5%; AÑO 1 2: 10%; AÑO 1 3: 10%; AÑO 1 4: 10%; AÑO 1 5: 20%; AÑO 1 6: 20%; AÑO 1 7: 25%
0 | 2.4 | 0 | Desmovilización de Fábrica de Dovelas y Obrador | 100% | Gl | 1 | 49425.1359 | 49425.1359 | 0 | 0 | 4 | 80839.5299 |  |  | AÑO 5 59: 10%; AÑO 5 60: 10%; AÑO 6 61: 20%; AÑO 6 62: 40%; AÑO 6 65: 10%; AÑO 6 66: 10%
0 | 2.5 | 0 | Movilización de tunelera y equipos túnel a Pozo Acceso 1 | 100% | Gl | 1 | 1813775.57 | 1813775.57 | 0 | 0 | 3 | 2966603.1603 |  |  | AÑO 1 1: 5%; AÑO 1 2: 5%; AÑO 1 3: 10%; AÑO 1 4: 10%; AÑO 1 5: 10%; AÑO 1 6: 10%; AÑO 1 7: 10%; AÑO 1 8: 10%; AÑO 1 9: 10%; AÑO 1 10: 10%; AÑO 1 11: 10%; AÑO 1 12: 0%
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | bar: AÑO 3 34
3 | 0 | 0 | Construcción de Pozos de Acceso |  | 0 | 0 | 0 | 0 | 0 | 0 | bar: AÑO 3 34
0 | 3.1 | 0 | Pozo Acceso 1 - Punta Carrasco | 100% | Gl. | 1 | 0 | 0 | 5391427.9879 | 2.354% | 9 | 8818195.3555 |  |  | AÑO 1 3: 8.125%; AÑO 1 4: 10.36%; AÑO 1 5: 15.48%; AÑO 1 6: 15.52%; AÑO 1 7: 20.21%; AÑO 1 8: 21.13%; AÑO 1 9: 4.736%; AÑO 1 10: 4.431%
0 | 3.2.1 | 0 | Pozo Acceso 2 - Calle Niceto Vega. (Salida Túnel 1) | 100% | GL | 1 | 0 | 0 | 1987418.6032 | 0.8679% | 5 | 3250612.924 |  |  | AÑO 2 23: 3.347%; AÑO 2 24: 27.09%; AÑO 3 25: 19.37%; AÑO 3 26: 19.51%; AÑO 3 27: 15.75%
| 3.2.2 |  | Obra Interna (Cámara de Conexión) |  | Gl | [5 empty] | 4 |  |  |  | AÑO 3 30: 2.958%; AÑO 3 31: 5.917%; AÑO 3 32: 2.564%; AÑO 3 33: 3.499%
0 | 3.3.1 | 0 | Pozo Acceso 3 - Calle Cuenca. (Salida Túnel 2) | 100% | GL | 1 | 0 | 0 | 2085265.7004 | 0.9106% | 5 | 3410651.1959 |  |  | AÑO 5 55: 3.347%; AÑO 5 56: 27.09%; AÑO 5 57: 19.37%; AÑO 5 58: 19.51%; AÑO 5 59: 15.75%
| 3.3.2 |  | Obra Interna (Cámara de Conexión) |  | GL | [5 empty] | 5 |  |  |  | AÑO 6 62: 2.958%; AÑO 6 63: 2.958%; AÑO 6 64: 2.958%; AÑO 6 65: 2.564%; AÑO 6 66: 3.499%
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | bar: AÑO 3 34
4 | 0 | 0 | Construcción de Túneles |  | 0 | 0 | 0 | 0 | 201091448.0109 | 87.81% | bar: AÑO 3 34
0 | 4.1 | 0 | Montaje y desmont. de equipamiento en Pozo 1 | 100% | Gl | 1 | 94294.89 | 94294.89 | 0 | 0 | 5 | 154228.2978 |  |  | AÑO 1 8: 10%; AÑO 1 9: 20%; AÑO 1 10: 20%; AÑO 1 11: 20%; AÑO 1 12: 10%; AÑO 5 60: 10%; AÑO 6 61: 10%
0 | 4.2 | 0 | Montaje de tunelera y back-up en Pozo 1 | 100% | Gl | 1 | 172988.98 | 172988.98 | 0 | 0 | 3 | 282939.9972 |  |  | AÑO 1 12: 20%; AÑO 2 13: 40%; AÑO 2 14: 40%
0 | 4.3 | 0 | Elaboración, transporte y colocación de dovelas | 100% | Anillo | 12012 | 6121.8506 | 73535668.8345 | 0 | 0 | 14+29 | 120274609.0352 | [16 empty] | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 1.19% |  |  | 1.19% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381%
0 | 4.4 | 0 | Excavacion túnel Ø 6.90 m Túnel 1 | 100% | Anillo | 3804 | 9304.8503 | 35395650.6987 | 0 | 0 | 14 | 57892967.0024 |  |  | AÑO 2 15: 7.407%; AÑO 2 16: 7.407%; AÑO 2 17: 7.407%; AÑO 2 18: 7.407%; AÑO 2 19: 7.407%; AÑO 2 20: 7.407%; AÑO 2 21: 7.407%; AÑO 2 22: 7.407%; AÑO 2 23: 7.407%; AÑO 2 24: 7.407%; AÑO 3 25: 7.407%; AÑO 3 26: 7.407%; AÑO 3 27: 7.407%; AÑO 3 28: 3.704%
0 | 4.5 | 0 | Desmontaje tunelera Pozo 2, traslado y mont. en Pozo 1 | 100% | Gl | 1 | 298903.63 | 298903.63 | 0 | 0 | 3 | 488885.4322 |  |  | AÑO 3 28: 25%; AÑO 3 29: 50%; AÑO 3 30: 25%
0 | 4.6 | 0 | Excavacion túnel Ø 6.90 m Túnel 2 | 100% | Anillo | 8208 | 9304.8503 | 76374211.6023 | 0 | 0 | 29 | 124917316.8127 |  |  | AÑO 3 31: 3.509%; AÑO 3 32: 3.509%; AÑO 3 33: 3.509%; AÑO 3 34: 3.509%; AÑO 3 35: 3.509%; AÑO 3 36: 3.509%; AÑO 4 37: 3.509%; AÑO 4 38: 3.509%; AÑO 4 39: 3.509%; AÑO 4 40: 3.509%; AÑO 4 41: 3.509%; AÑO 4 42: 3.509%; AÑO 4 43: 3.509%; AÑO 4 44: 3.509%; AÑO 4 45: 3.509%; AÑO 4 46: 3.509%; AÑO 4 47: 3.509%; AÑO 4 48: 3.509%; AÑO 5 49: 3.509%; AÑO 5 50: 3.509%; AÑO 5 51: 3.509%; AÑO 5 52: 3.509%; AÑO 5 53: 3.509%; AÑO 5 54: 3.509%; AÑO 5 55: 3.509%; AÑO 5 56: 3.509%; AÑO 5 57: 3.509%; AÑO 5 58: 3.509%; AÑO 5 59: 1.754%
0 | 4.7 | 0 | Desmontaje tunelera Pozo C, traslado a Puerto | 100% | Gl | 1 | 248777.41 | 248777.41 | 0 | 0 | 3 | 406899.2123 |  |  | AÑO 5 59: 25%; AÑO 5 60: 50%; AÑO 6 61: 25%
0 | 4.8 | 0 | Transporte suelo proveniente túnel a dispos. Final (9km) | 100% | km-m3 | 8245696.2916 | 1.2488 | 10297362.2462 | 0 | 0 | 14+29 | 16842319.3518 | [16 empty] | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 1.19% |  |  | 1.19% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381%
0 | 4.9 | 0 | Tratamiento de suelo en cruce con interferencias | 100% | Un. | 6 | 144284.5465 | 865707.2792 | 0 | 0 | 6 | 1415946.9302 |  |  | AÑO 2 17: 16.67%; AÑO 2 20: 16.67%; AÑO 3 26: 16.67%; AÑO 3 33: 16.67%; AÑO 4 37: 16.67%; AÑO 4 41: 16.67%
0 | 4.10 | 0 | Instrumentación para Auscultación | 100% | Gl | 1 | 2000000 | 2000000 | 0 | 0 | 31 | 3271191 |  |  | AÑO 2 16: 3.2%; AÑO 2 18: 3.2%; AÑO 2 19: 3.2%; AÑO 2 20: 3.2%; AÑO 2 22: 3.2%; AÑO 2 23: 3.2%; AÑO 2 24: 3.2%; AÑO 3 25: 3.2%; AÑO 3 26: 3.2%; AÑO 3 28: 3.2%; AÑO 3 31: 3.2%; AÑO 3 33: 3.2%; AÑO 3 35: 3.2%; AÑO 4 37: 3.2%; AÑO 4 39: 3.2%; AÑO 4 40: 3.2%; AÑO 4 41: 3.2%; AÑO 4 42: 3.2%; AÑO 4 43: 3.2%; AÑO 4 45: 3.2%; AÑO 4 47: 4%; AÑO 5 49: 3.2%; AÑO 5 50: 3.2%; AÑO 5 51: 3.2%; AÑO 5 52: 3.2%; AÑO 5 53: 3.2%; AÑO 5 54: 3.2%; AÑO 5 55: 3.2%; AÑO 5 57: 3.2%; AÑO 5 58: 3.2%; AÑO 5 59: 3.2%
| 4.11 | 0 | Sellado de nichos para bulones | 100% | anillo | 12012 | 150.5064 | 1807882.44 | 0 | 0 | 14+29 | 2956964.3834 | [16 empty] | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 1.19% |  |  | 1.19% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381% | 2.381%
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | Estructuras de derivación |  | Gl | 0 | 0 | 0 | 0 | 0
0 | 5.1 | 0 | Estructura de derivación Calle Niceto Vega | 100% | Gl | 1 | 0 | 0 | 1355266.2594 | 0.5918% | 14 | 2216667.3952 |  |  | AÑO 2 19: 2.531%; AÑO 2 20: 6.334%; AÑO 2 21: 8.887%; AÑO 2 22: 7.094%; AÑO 2 23: 6.799%; AÑO 2 24: 8.2%; AÑO 3 25: 5.329%; AÑO 3 26: 5.822%; AÑO 3 27: 1.423%; AÑO 3 28: 9.966%; AÑO 3 29: 1.434%; AÑO 3 30: 9.046%; AÑO 3 31: 11.04%; AÑO 3 32: 16.1%
0 | 5.2 | 0 | Estructura de derivación Calle Cuenca | 100% | Gl | 1 | 0 | 0 | 847875.1931 | 0.3703% | 14 | 1386780.8503 |  |  | AÑO 5 52: 12.02%; AÑO 5 53: 11.95%; AÑO 5 54: 9.93%; AÑO 5 55: 6.093%; AÑO 5 56: 6.315%; AÑO 5 57: 6.799%; AÑO 5 58: 2.85%; AÑO 5 59: 2.209%; AÑO 5 60: 3.707%; AÑO 6 61: 4.11%; AÑO 6 62: 7.121%; AÑO 6 63: 10.71%; AÑO 6 64: 10.69%; AÑO 6 65: 5.505%
0 | 5.3 | 0 | Estructura de derivación Calle H. Pueyrredón | 100% | Gl | 1 | 0 | 0 | 1496625.1807 | 0.6535% | 14 | 2447873.4107 |  |  | AÑO 4 41: 1.584%; AÑO 4 42: 8.42%; AÑO 4 43: 8.178%; AÑO 4 44: 11.81%; AÑO 4 45: 12.28%; AÑO 4 46: 16.46%; AÑO 4 47: 9.107%; AÑO 4 48: 3.719%; AÑO 5 49: 6.394%; AÑO 5 50: 6.785%; AÑO 5 51: 6.459%; AÑO 5 52: 2.079%; AÑO 5 53: 1.793%; AÑO 5 54: 4.93%
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | Obra de descarga y bombeo en Pozo 1 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 6.1 | 0 | Obra Interna Cámara 1 y Canal de Descarga Túnel 1 | 100% | Gl. | 1 | 0 | 0 | 2441626.7813 | 1.066% | 6 | 3993513.7761 |  |  | AÑO 3 28: 10%; AÑO 3 29: 15%; AÑO 3 30: 18%; AÑO 3 31: 20%; AÑO 3 32: 20%; AÑO 3 33: 17%
0 | 6.2 | 0 | Obra Interna Cámara 2, Canal de Descarga Túnel 2 y Cámara de Bombas | 100% | Gl | 1 | 0 | 0 | 4040323.8086 | 1.764% | 8 | 6608335.4399 |  |  | AÑO 5 59: 5.392%; AÑO 5 60: 7%; AÑO 6 61: 8%; AÑO 6 62: 8%; AÑO 6 63: 9.171%; AÑO 6 64: 11.48%; AÑO 6 65: 14.53%; AÑO 6 66: 36.43%
0 | 6.3 | 0 | Tablestacado para el Canal de Descarga | 100% | Gl | 0 | 0 | 0 | 1083825.8659 | 0.4733% | 3 | 1772700.7091 |  |  | AÑO 3 27: 20%; AÑO 3 28: 30%; AÑO 3 29: 50%
0 | 6.4 | 0 | Trabajos Finales en Superficie | 100% | Gl | 0 | 0 | 0 | 214246.7026 | 0.09356% | 5 | 350420.9427 |  |  | AÑO 6 62: 10%; AÑO 6 63: 20%; AÑO 6 64: 20%; AÑO 6 65: 20%; AÑO 6 66: 30%
7 | 0 | 0 | Obras de Ventilación de túneles |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 7.1 | 0 | Ventilación Túnel 1 | 100% | Gl. | 1 | 0 | 0 | 55257.2042 | 0.02413% | 6 | 90378.4345 |  |  | AÑO 2 22: 15%; AÑO 2 23: 19%; AÑO 2 24: 31%; AÑO 3 25: 35%
0 | 7.2 | 0 | Ventilación Túnel 2 | 100% | Gl. | 1 | 0 | 0 | 57900.5007 | 0.02528% | 6 | 94701.7984 |  |  | AÑO 4 46: 15%; AÑO 4 47: 19%; AÑO 4 48: 31%; AÑO 5 49: 35%
|  | 0 |  |  |  | 0 | 0 | 229000000 | 229000000 | 99.63%
|  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | 0 |  |  |  | 0 | 0 | 43510000 | 272510000 | 0
|  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | 0 |  |  |  | 0 | 0 | 5450200 | 277960200 | 0
|  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | 0 |  |  |  | 0 | 0 | 27796020 | 305756220 | 0
|  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | 0 |  |  |  | 0 | 0 | 68795149.5 | 374551369.5 | 0
|  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | TUNELES | CERTIFICACION MENSUAL |  | 1.0948 | 1.2898 | 2.2236 | 1.2843 | 1.9084 | 1.7135 | 2.2135 | 1.8791 | 1.0418 | 1.5094 | 1.5141 | 0.10286 | 0.11318 | 0.11318 | 7.5531 | 7.6577 | 7.789 | 7.6577 | 7.7138 | 8.0341 | 7.7501 | 7.8216 | 7.9264 | 8.7402 | 8.6207 | 8.8758 | 8.467 | 5.1555 | 1.7616 | 1.1377 | 7.3558 | 8.8866 | 8.7811 | 7.6478 | 7.7524 | 7.6478 | 7.9884 | 7.8455 | 7.7524 | 7.7524 | 8.0272 | 7.9585 | 7.9526 | 7.9368 | 8.053 | 8.058 | 8.0113 | 7.7597 | 7.9267 | 8.1377 | 8.126 | 7.9701 | 7.962 | 8.0108 | 7.9511 | 8.6591 | 8.5074 | 8.4574 | 6.5948 | 0.72552 | 0.70355 | 0.79571 | 0.92548 | 1.0776 | 1.2024 | 2.6397 | 0 | 0 | 0 | 0 | 0
|  | 0 |  |  | 0 | 0 | 0 | 374551369.5 | 0 | 163.6% |  | SEC/ T CORTO | EN MILLONES DE PESOS |  | 0.014226 | 0.014226 | 0.44016 | 0.50889 | 0.49198 | 0.68108 | 0.67655 | 0.73644 | 0.014226 | 0.7214 | 0.7214 | 0.81462 | 0.82063 | 0.69977 | 0.54785 | 0.54785 | 0.54785 | 0.28104 | 0.40335 | 1.3667 | 1.7432 | 1.0311 | 1.3038 | 1.6328 | 2.2244 | 1.0096 | 1.2592 | 1.2592 | 1.3185 | 1.1875 | 1.3389 | 1.455 | 1.2924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 |  | SEC/ T LARGO |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1577 | 1.3315 | 0.59732 | 0.86123 | 1.0681 | 0.88976 | 0.94388 | 0.61858 | 1.0222 | 0.59972 | 0.79883 | 0.33443 | 0.76801 | 1.5522 | 1.5522 | 1.5522 | 1.6785 | 2.2643 | 3.4916 | 3.2408 | 2.7817 | 1.5778 | 1.4864 | 2.1653 | 2.131 | 2.921 | 2.7195 | 2.7613 | 2.09 | 2.7987 | 2.7538 | 3.0668 | 3.3774
[6 empty] | 0 | 0 | 0 | 0 | 0
[9 empty] | 18727568.475 |  |  | EG OBRA TOT |  |  | 1.1091 | 1.304 | 2.6638 | 1.7932 | 2.4004 | 2.3946 | 2.8901 | 2.6155 | 1.056 | 2.2308 | 2.2356 | 0.91748 | 0.93381 | 0.81294 | 8.1009 | 8.2056 | 8.3369 | 7.9388 | 8.1172 | 9.4008 | 9.4933 | 8.8527 | 9.2302 | 10.373 | 10.8452 | 9.8855 | 9.7262 | 6.4147 | 3.0802 | 2.3252 | 8.6948 | 10.3416 | 10.0734 | 8.8054 | 9.0839 | 8.2451 | 8.8497 | 8.9136 | 8.6422 | 8.6963 | 8.6458 | 8.9807 | 8.5523 | 8.7357 | 8.3874 | 8.826 | 9.5634 | 9.3119 | 9.4789 | 9.8162 | 10.3902 | 11.4616 | 11.2029 | 10.7926 | 9.5288 | 10.1455 | 10.6726 | 10.5884 | 9.5158 | 3.445 | 3.4649 | 2.8857 | 3.7242 | 3.8314 | 4.2692 | 6.0171 | 0 | 0 | 0 | 0 | 0
[9 empty] | 4.549 |  |  | SUP TUNEL |  |  | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375 | 0.28375
[12 empty] | SUP SEC |  |  | 0.00071128 | 0.00071128 | 0.022008 | 0.025445 | 0.024599 | 0.034054 | 0.033827 | 0.036822 | 0.00071128 | 0.03607 | 0.03607 | 0.040731 | 0.041032 | 0.034988 | 0.027393 | 0.027393 | 0.027393 | 0.014052 | 0.020167 | 0.068334 | 0.087162 | 0.051555 | 0.065189 | 0.081641 | 0.11122 | 0.050482 | 0.062961 | 0.062961 | 0.065927 | 0.059374 | 0.066947 | 0.072751 | 0.064619 | 0.057884 | 0.066575 | 0.029866 | 0.043062 | 0.053404 | 0.044488 | 0.047194 | 0.030929 | 0.05111 | 0.029986 | 0.039941 | 0.016722 | 0.038401 | 0.07761 | 0.07761 | 0.07761 | 0.083923 | 0.11321 | 0.17458 | 0.16204 | 0.13909 | 0.078888 | 0.074319 | 0.10826 | 0.10655 | 0.14605 | 0.13598 | 0.13807 | 0.1045 | 0.13993 | 0.13769 | 0.15334 | 0.16887 | 0 | 0 | 0 | 0 | 0
[12 empty] | TOTAL CERT M |  |  | 1.3935 | 1.5885 | 2.9696 | 2.1024 | 2.7088 | 2.7124 | 3.2077 | 2.9361 | 1.3405 | 2.5506 | 2.5554 | 1.242 | 1.2586 | 1.1317 | 8.4121 | 8.5167 | 8.648 | 8.2366 | 8.4211 | 9.7529 | 9.8642 | 9.188 | 9.5792 | 10.7384 | 11.2401 | 10.2197 | 10.0729 | 6.7614 | 3.4298 | 2.6683 | 9.0455 | 10.6981 | 10.4218 | 9.1471 | 9.4343 | 8.5587 | 9.1765 | 9.2508 | 8.9704 | 9.0273 | 8.9605 | 9.3156 | 8.8661 | 9.0593 | 8.6879 | 9.1482 | 9.9248 | 9.6732 | 9.8403 | 10.1838 | 10.7872 | 11.9199 | 11.6487 | 11.2154 | 9.8915 | 10.5036 | 11.0646 | 10.9787 | 9.9456 | 3.8648 | 3.8867 | 3.2739 | 4.1478 | 4.2528 | 4.7063 | 6.4698 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 |  |  | 0.2895% | 0.33% | 0.6169% | 0.4367% | 0.5627% | 0.5634% | 0.6663% | 0.6099% | 0.2785% | 0.5298% | 0.5308% | 0.258% | 0.2614% | 0.2351% | 1.747% | 1.769% | 1.796% | 1.711% | 1.749% | 2.026% | 2.049% | 1.909% | 1.99% | 2.231% | 2.335% | 2.123% | 2.092% | 1.405% | 0.7125% | 0.5543% | 1.879% | 2.222% | 2.165% | 1.9% | 1.96% | 1.778% | 1.906% | 1.922% | 1.863% | 1.875% | 1.861% | 1.935% | 1.842% | 1.882% | 1.805% | 1.9% | 2.062% | 2.009% | 2.044% | 2.115% | 2.241% | 2.476% | 2.42% | 2.33% | 2.055% | 2.182% | 2.298% | 2.281% | 2.066% | 0.8028% | 0.8074% | 0.6801% | 0.8616% | 0.8834% | 0.9776% | 1.344% | 0% | 0% | 0% | 0% | 0%
[15 empty] | 0.28948 | 0.61946 | 1.2363 | 1.6731 | 2.2357 | 2.7992 | 3.4655 | 4.0754 | 4.3539 | 4.8837 | 5.4145 | 5.6725 | 5.934 | 6.1691 | 7.9165 | 9.6857 | 11.4821 | 13.1931 | 14.9424 | 16.9684 | 19.0175 | 20.9261 | 22.916 | 25.1467 | 27.4816 | 29.6045 | 31.697 | 33.1015 | 33.814 | 34.3683 | 36.2473 | 38.4696 | 40.6345 | 42.5347 | 44.4944 | 46.2723 | 48.1786 | 50.1002 | 51.9637 | 53.8389 | 55.7002 | 57.6354 | 59.4771 | 61.359 | 63.1638 | 65.0641 | 67.1258 | 69.1352 | 71.1793 | 73.2948 | 75.5356 | 78.0118 | 80.4315 | 82.7613 | 84.8161 | 86.998 | 89.2964 | 91.577 | 93.643 | 94.4458 | 95.2532 | 95.9333 | 96.7949 | 97.6784 | 98.656 | 100
[12 empty] | 0 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66
[15 empty] | 2.799% | [5 empty] | 2.873% | [5 empty] | 7.521% | [5 empty] | 11.95% | [5 empty] | 9.222% | [5 empty] | 11.9% | [5 empty] | 11.36% | [5 empty] | 11.5% | [5 empty] | 13.63% | [5 empty] | 11.68% | [5 empty] | 5.554%
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!

## Actividades
¦
SECUNDARIO | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
|  | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5 | 11 | 11.5 | 12 | 12.5 | 13 | 13.5 | 14 | 14.5 | 15 | 15.5 | 16 | 16.5 | 17 | 17.5 | 18 | 18.5 | 19 | 19.5 | 20 | 20.5 | 21 | 21.5 | 22 | 22.5 | 23 | 23.5 | 24 | 24.5 | 25 | 25.5 | 26 | 26.5 | 27 | 27.5 | 28 | 28.5 | 29 | 29.5 | 30 | 30.5 | 31 | 31.5 | 32 | 32.5 | 33 | 33.5 | 34 | 34.5 | 35 | 35.5 | 36 | 36.5 | 37 | 37.5 | 38 | 38.5 | 39 | 39.5 | 40 | 40.5 | 41 | 41.5 | 42 | 42.5 | 43 | 43.5 | 44 | 44.5 | 45 | 45.5 | 46 | 46.5 | 47 | 47.5 | 48 | 48.5
Ramal Lugones | 6 | [44 empty] | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578
[46 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Casares | 3.5 | [56 empty] | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal F. Alcorta | 4.5 | [63 empty] | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521
[65 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Sur | 3.5 | [43 empty] | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Infanta Isabel | 2 | [46 empty] | 115462.5826 | 115462.5826 | 115462.5826 | 115462.5826
[48 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Norte | 0.5 | [46 empty] | 177502.3263
0.5
Ramal Libertador | 4 | [39 empty] | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707
[41 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sinclair | 1.5 | [44 empty] | 69347.9837 | 69347.9837 | 69347.9837
[46 empty] | 0.5 | 0.5 | 0.5
Ramal Arévalo | 2 | [24 empty] | 126822.0533 | 126822.0533 | 126822.0533 | 126822.0533
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Matienzo | 1 | [24 empty] | 58015.7901 | 58015.7901
[26 empty] | 0.5 | 0.5
Ramal Godoy Cruz | 2 | [28 empty] | 84668.3453 | 84668.3453 | 84668.3453 | 84668.3453
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Olleros | 3 | [28 empty] | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santa Fe | 1.5 | [34 empty] | 56734.4507 | 56734.4507 | 56734.4507
[36 empty] | 0.5 | 0.5 | 0.5
Ramal Fitz Roy | 0.5 | [37 empty] | 62734.9089
0.5
Ramal Bonpland | 1.5 | [38 empty] | 76457.031 | 76457.031 | 76457.031
[40 empty] | 0.5 | 0.5 | 0.5
Ramal Nicaragua | 1 | [24 empty] | 56046.5514 | 56046.5514
[26 empty] | 0.5 | 0.5
Ramal Costa Rica | 7 | [56 empty] | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Gurruchaga | 1 | [62 empty] | 45149.4816 | 45149.4816
[64 empty] | 0.5 | 0.5
Ramal Armenia | 1 | [65 empty] | 48214.397 | 48214.397
[67 empty] | 0.5 | 0.5
Ramal J. Alvarez | 0.5 | [69 empty] | 117835.6189
0.5
Ramal Lavalleja I | 1.5 | [69 empty] | 73082.7908 | 73082.7908 | 73082.7908
[71 empty] | 0.5 | 0.5 | 0.5
Ramal Cabrera | 1 | [49 empty] | 43239.6469 | 43239.6469
[51 empty] | 0.5 | 0.5
Ramal Niceto Vega Sur | 2 | [49 empty] | 72285.9116 | 72285.9116 | 72285.9116 | 72285.9116
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Niceto Vega Norte | 6 | [54 empty] | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742
[56 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Castillo | 0.5 | [65 empty] | 55621.4443
0.5
Ramal Acevedo | 1.5 | [51 empty] | 68757.9133 | 68757.9133 | 68757.9133
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Lavalleja II | 1 | [51 empty] | 64651.0238 | 64651.0238
[53 empty] | 0.5 | 0.5
Ramal Loyola | 6.5 | [59 empty] | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699
[61 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Velazco | 17 | [38 empty] | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808
[40 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal A. Gallardo | 0.5 | [61 empty] | 59400.5619
0.5
Ramal Lambaré | 1 | [65 empty] | 48647.7295 | 48647.7295
[67 empty] | 0.5 | 0.5
Ramal Estivao | 1 | [67 empty] | 79358.416 | 79358.416
[69 empty] | 0.5 | 0.5
Ramal Vera | 1 | [49 empty] | 46673.1076 | 46673.1076
[51 empty] | 0.5 | 0.5
Ramal Corrientes | 5 | [66 empty] | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707
[68 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Dorrego | 0.5 | [75 empty] | 64033.4167
0.5
Sumideros a Ramales Exist | 19 | [24 empty] | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Murillo | 2 | [68 empty] | 196896.1029 | 196896.1029 | 196896.1029 | 196896.1029 | [25 empty] | 31274527.3213
[70 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Muñecas Sur | 1.5 | [66 empty] | 68753.3919 | 68753.3919 | 68753.3919
[68 empty] | 0.5 | 0.5 | 0.5
Ramal Muñecas Norte | 1 | [68 empty] | 84870.5482 | 84870.5482
[70 empty] | 0.5 | 0.5
Ramal Darwin | 1 | [70 empty] | 34080.6876 | 34080.6876
[72 empty] | 0.5 | 0.5
Ramal M. Rosas | 4.5 | [52 empty] | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Caldas | 3 | [61 empty] | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223
[63 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santos Dumont | 1 | [67 empty] | 56626.5552 | 56626.5552
[69 empty] | 0.5 | 0.5
Ramal H. Pueyrredón | 8 | [70 empty] | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Tres Arroyos | 1.5 | [74 empty] | 56762.0448 | 56762.0448 | 56762.0448
[76 empty] | 0.5 | 0.5 | 0.5
Ramal Olaya | 1.5 | [77 empty] | 83417.4807 | 83417.4807 | 83417.4807
[79 empty] | 0.5 | 0.5 | 0.5
Ramal Rojas | 1 | [76 empty] | 39688.4802 | 39688.4802
[78 empty] | 0.5 | 0.5
Ramal Franklin | 1 | [83 empty] | 47703.7952 | 47703.7952
[85 empty] | 0.5 | 0.5
Ramal Arengreen | 5 | [86 empty] | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405
[88 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Aranguren | 1 | [94 empty] | 41661.2822 | 41661.2822
[96 empty] | 0.5 | 0.5
Ramal Cucha Cucha Sur | 2.5 | [50 empty] | 76191.728 | 76191.728 | 76191.728 | 76191.728 | 76191.728
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cucha Cucha Norte | 15.5 | [43 empty] | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Maturín | 1 | [61 empty] | 71493.528 | 71493.528
[63 empty] | 0.5 | 0.5
Ramal Constituyentes | 0.5 | [70 empty] | 38423.8726
0.5
Ramal Paysandú | 1 | [50 empty] | 46136.1796 | 46136.1796
[52 empty] | 0.5 | 0.5
Ramal San Martín | 5.5 | [74 empty] | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795
[76 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Camarones I | 5.5 | [85 empty] | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057
[87 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sánchez | 1 | [88 empty] | 35323.2858 | 35323.2858
[90 empty] | 0.5 | 0.5
Ramal A. Lamas | 1 | [91 empty] | 46983.3613 | 46983.3613
[93 empty] | 0.5 | 0.5
Ramal Seguí | 0.5 | [50 empty] | 77342.6992
0.5
Ramal Mendez de Andés | 5.5 | [49 empty] | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Calcena | 2 | [52 empty] | 59879.5762 | 59879.5762 | 59879.5762 | 59879.5762
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bogotá | 1.5 | [58 empty] | 76937.3008 | 76937.3008 | 76937.3008
[60 empty] | 0.5 | 0.5 | 0.5
Ramal Boyacá Sur | 1 | [52 empty] | 36412.3973 | 36412.3973
[54 empty] | 0.5 | 0.5
Ramal Boyacá Norte | 1.5 | [50 empty] | 50400.3835 | 50400.3835 | 50400.3835
[52 empty] | 0.5 | 0.5 | 0.5
Ramal Caracas | 18 | [60 empty] | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644
[62 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Biarritz | 1.5 | [75 empty] | 71933.6659 | 71933.6659 | 71933.6659
[77 empty] | 0.5 | 0.5 | 0.5
Ramal Carranza | 1 | [78 empty] | 46882.847 | 46882.847
[80 empty] | 0.5 | 0.5
Ramal Santo Tomé I | 0.5 | [84 empty] | 47709.0702
0.5
Ramal Empedrado | 1 | [89 empty] | 95763.2228 | 95763.2228
[91 empty] | 0.5 | 0.5
Ramal Zamudio | 2 | [92 empty] | 140547.3977 | 140547.3977 | 140547.3977 | 140547.3977
[94 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bufano | 1 | [55 empty] | 43875.9928 | 43875.9928
[57 empty] | 0.5 | 0.5
Ramal Bolivia Sur | 1.5 | [59 empty] | 111763.9143 | 111763.9143 | 111763.9143
[61 empty] | 0.5 | 0.5 | 0.5
Ramal Bolivia Norte | 0.5 | [61 empty] | 58219.7546
0.5
Ramal Terrada | 2 | [73 empty] | 63991.8159 | 63991.8159 | 63991.8159 | 63991.8159
[75 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Argerich Sur | 1 | [76 empty] | 48388.6905 | 48388.6905
[78 empty] | 0.5 | 0.5
Ramal Argerich Norte | 8.5 | [48 empty] | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Beláustegui | 1.5 | [51 empty] | 52496.3873 | 52496.3873 | 52496.3873
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Cesar Díaz | 1 | [57 empty] | 38903.9081 | 38903.9081
[59 empty] | 0.5 | 0.5
Ramal Camarones II | 1.5 | [60 empty] | 51716.7099 | 51716.7099 | 51716.7099
[62 empty] | 0.5 | 0.5 | 0.5
Ramal García I | 2 | [65 empty] | 67552.1337 | 67552.1337 | 67552.1337 | 67552.1337
[67 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Campana | 1 | [69 empty] | 42313.5624 | 42313.5624
[71 empty] | 0.5 | 0.5
Ramal Helguera | 1 | [70 empty] | 40587.2993 | 40587.2993
[72 empty] | 0.5 | 0.5
Ramal Galicia | 1.5 | [74 empty] | 44555.9821 | 44555.9821 | 44555.9821
[76 empty] | 0.5 | 0.5 | 0.5
Ramal E. González I | 1.5 | [78 empty] | 55051.6867 | 55051.6867 | 55051.6867
[80 empty] | 0.5 | 0.5 | 0.5
Ramal Vilardebó I | 7 | [50 empty] | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Vilardebó II | 1 | [62 empty] | 38173.1042 | 38173.1042
[64 empty] | 0.5 | 0.5
Ramal Bahía Blanca | 1 | [50 empty] | 61446.7283 | 61446.7283
[52 empty] | 0.5 | 0.5
Ramal E. Lamarca | 0.5 | [66 empty] | 74730.378
0.5
Ramal Chivilcoy | 0.5 | [67 empty] | 100452.7646
0.5
Ramal Sanabria | 1 | [68 empty] | 75715.9069 | 75715.9069
[70 empty] | 0.5 | 0.5
Ramal Segurola | 13 | [70 empty] | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal R. E. De San Martín | 1 | [73 empty] | 53222.1685 | 53222.1685
[75 empty] | 0.5 | 0.5
Ramal E. González II | 1 | [86 empty] | 40335.8049 | 40335.8049
[88 empty] | 0.5 | 0.5
Ramal Santo Tomé II | 1 | [94 empty] | 53780.3587 | 53780.3587
[96 empty] | 0.5 | 0.5
Ramal Goya | 0.5 | [69 empty] | 49125.2383
0.5
Ramal Carrasco | 2.5 | [75 empty] | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774
[77 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez II | 5.5 | [70 empty] | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez I | 3.5 | [81 empty] | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132
[83 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cervantes Sur | 1 | [52 empty] | 63507.7688 | 63507.7688
[54 empty] | 0.5 | 0.5
Ramal Cervantes Norte | 9 | [52 empty] | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Marcos Sastre | 1 | [70 empty] | 71074.5565 | 71074.5565
[72 empty] | 0.5 | 0.5
Ramal Calderón de la Barca | 1 | [50 empty] | 49190.8136 | 49190.8136
[52 empty] | 0.5 | 0.5
Ramal Milton | 1 | [53 empty] | 47806.7739 | 47806.7739
[55 empty] | 0.5 | 0.5
Ramal Virgilio | 1 | [56 empty] | 62504.4586 | 62504.4586
[58 empty] | 0.5 | 0.5
Ramal Victor Hugo | 1 | [59 empty] | 60748.8644 | 60748.8644
[61 empty] | 0.5 | 0.5
Ramal Camarones III | 1 | [62 empty] | 93965.0121 | 93965.0121
[64 empty] | 0.5 | 0.5
Ramal García II | 1 | [65 empty] | 53916.9164 | 53916.9164
[67 empty] | 0.5 | 0.5
Ramal Peralta | 1 | [50 empty] | 49831.2481 | 49831.2481
[52 empty] | 0.5 | 0.5
Ramal Alvarez Jonte | 2 | [52 empty] | 120654.8098 | 120654.8098 | 120654.8098 | 120654.8098
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Barragán | 1 | [56 empty] | 41900.42 | 41900.42
[58 empty] | 0.5 | 0.5
Ramal Cuzco Sur | 6.5 | [83 empty] | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539
[85 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Rivadavia I | 1 | [89 empty] | 84495.646 | 84495.646
[91 empty] | 0.5 | 0.5
Ramal Rivadavia II | 1.5 | [91 empty] | 112932.1063 | 112932.1063 | 112932.1063
[93 empty] | 0.5 | 0.5 | 0.5
Ramal Cuzco Norte | 0.5 | [95 empty] | 70925.8541
0.5
Sumideros a Ramales Exist | 24 | [48 empty] | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
TUNEL | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
Tunel Corto | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251907.2182 | 251907.2182 | 137844.8767 | 137844.8767 | 199034.9041 | 199034.9041 | 199034.9041 | 199034.9041 | 114366.5587 | 114366.5587 | 67757.2741 | 67757.2741 | 67757.2741 | 73757.7323 | 446414.5352 | 595013.206 | 595013.206 | 518556.1749 | 518556.1749 | 664370.0777 | 865187.3192 | 865187.3192 | 1158152.2281 | 762703.2474 | 762703.2474 | 924901.9135 | 663625.428 | 707121.6107 | 707121.6107 | 570184.6753 | 643503.1362 | 643503.1362 | 853771.3893 | 853771.3893 | 853771.3893 | 1012911.6593 | 1012911.6593 | 1072312.2212 | 1047038.3175 | 1098671.5868 | 1053522.1052 | 1206005.676 | 1096766.5282 | 1079262.8178 | 1079262.8178 | 1190822.8114 | 826316.0644 | 826316.0644 | 88458.6707 | 88458.6707 | 88458.6707 | 152492.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 251908.7182 | 251908.7182 | 137845.3767 | 137845.3767 | 199035.9041 | 199035.9041 | 199035.9041 | 199035.9041 | 114367.0587 | 114367.0587 | 67757.7741 | 67757.7741 | 67757.7741 | 73758.2323 | 446415.5352 | 595014.706 | 595014.706 | 518557.1749 | 518557.1749 | 664371.5777 | 865189.8192 | 865189.8192 | 1158155.7281 | 762705.2474 | 762705.2474 | 924905.4135 | 663627.928 | 707124.1107 | 707124.1107 | 570186.1753 | 643504.6362 | 643504.6362 | 853773.3893 | 853773.3893 | 853773.3893 | 1012914.1593 | 1012914.1593 | 1072315.2212 | 1047041.3175 | 1098674.5868 | 1053524.6052 | 1206009.676 | 1096770.0282 | 1079265.8178 | 1079265.8178 | 1190826.3114 | 826318.5644 | 826318.5644 | 88459.1707 | 88459.1707 | 88459.1707 | 152493.0874
Tunel Largo | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 445749.6926 | 621665.8358 | 1230463.8272 | 1205617.5153 | 1665420.3985 | 1662826.7889 | 1510410.2355 | 1430287.7264 | 1354158.219 | 1349186.1344 | 1321718.5566 | 1455327.4271 | 1577653.4582 | 1622045.1942 | 1584199.6417 | 1460989.4038 | 1130593.0764 | 1040504.2599 | 1183988.0298 | 1029202.6329 | 1286232.4263 | 1184739.1462 | 1685078.0406 | 1604340.6056 | 1261701.9593 | 1378915.9437 | 1371249.4259 | 1467438.9007 | 1555516.0714 | 1473623.7094 | 1415547.4064 | 1415547.4064 | 1207769.1013 | 1022351.2297 | 1022351.2297 | 1220793.6788 | 1268502.749 | 1181029.5098 | 1148856.633 | 1148856.633 | 1048020.5007 | 1228279.3695 | 1192956.0837 | 1172612.6824 | 1313160.0802 | 1266176.7189 | 1248686.2535 | 1319612.1076
[45 empty] | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 421347.9907 | 597264.6339 | 1206066.6253 | 1181220.3134 | 1641024.1966 | 1638430.587 | 1486012.5336 | 1405889.5245 | 1329760.0171 | 1324787.9324 | 1297319.8547 | 1430929.2252 | 1553255.7563 | 1597647.4923 | 1559801.9397 | 1436590.7018 | 1106192.8744 | 1016104.558 | 1159589.3279 | 1004803.4309 | 1261834.2244 | 1160340.4442 | 1660680.8386 | 1579942.4037 | 1237301.7573 | 1354516.7417 | 1346851.2239 | 1443041.1988 | 1531119.3695 | 1449226.0075 | 1391149.2045 | 1391149.2045 | 1183369.3994 | 997951.0278 | 997951.0278 | 1196394.4768 | 1244104.047 | 1156629.8078 | 1124457.431 | 1124457.431 | 1023620.7987 | 1203880.6676 | 1168556.8818 | 1148213.4805 | 1288761.3782 | 1241777.5169 | 1224287.5515 | 1295213.9056
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25191 | 0.25191 | 0.13784 | 0.13784 | 0.19903 | 0.19903 | 0.19903 | 0.19903 | 0.11437 | 0.11437 | 0.067757 | 0.067757 | 0.067757 | 0.073758 | 0.44641 | 0.59501 | 0.59501 | 0.51856 | 0.51856 | 0.87416 | 1.075 | 1.075 | 1.3679 | 0.97249 | 1.2085 | 1.5466 | 1.8941 | 1.9127 | 2.3725 | 2.233 | 2.1539 | 2.0738 | 2.2079 | 2.203 | 2.1755 | 2.4682 | 2.5906 | 2.6944 | 2.6312 | 2.5597 | 2.1841 | 2.2465 | 2.2808 | 2.1085 | 2.3655 | 2.3756 | 2.5114 | 2.4307 | 1.3502 | 1.4674 | 1.4597 | 1.6199 | 1.5555 | 1.4736 | 1.4155 | 1.4155 | 1.2078 | 1.0224 | 1.0224 | 1.2208 | 1.2685 | 1.181 | 1.1489 | 1.1489 | 1.048 | 1.2283 | 1.193 | 1.1726 | 1.3132 | 1.2662 | 1.2487 | 1.3196 | 94315426.599

## A
SECUNDARIO | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
|  | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5 | 11 | 11.5 | 12 | 12.5 | 13 | 13.5 | 14 | 14.5 | 15 | 15.5 | 16 | 16.5 | 17 | 17.5 | 18 | 18.5 | 19 | 19.5 | 20 | 20.5 | 21 | 21.5 | 22 | 22.5 | 23 | 23.5 | 24 | 24.5 | 25 | 25.5 | 26 | 26.5 | 27 | 27.5 | 28 | 28.5 | 29 | 29.5 | 30 | 30.5 | 31 | 31.5 | 32 | 32.5 | 33 | 33.5 | 34 | 34.5 | 35 | 35.5 | 36 | 36.5 | 37 | 37.5 | 38 | 38.5 | 39 | 39.5 | 40 | 40.5 | 41 | 41.5 | 42 | 42.5 | 43 | 43.5 | 44 | 44.5 | 45 | 45.5 | 46 | 46.5 | 47 | 47.5 | 48 | 48.5
Ramal Lugones | 6 | [44 empty] | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578
[46 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Casares | 3.5 | [56 empty] | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal F. Alcorta | 4.5 | [63 empty] | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521
[65 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Sur | 3.5 | [43 empty] | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Infanta Isabel | 2 | [46 empty] | 115462.5826 | 115462.5826 | 115462.5826 | 115462.5826
[48 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Norte | 0.5 | [46 empty] | 177502.3263
0.5
Ramal Libertador | 4 | [39 empty] | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707
[41 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sinclair | 1.5 | [44 empty] | 69347.9837 | 69347.9837 | 69347.9837
[46 empty] | 0.5 | 0.5 | 0.5
Ramal Arévalo | 2 | [24 empty] | 126822.0533 | 126822.0533 | 126822.0533 | 126822.0533
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Matienzo | 1 | [24 empty] | 58015.7901 | 58015.7901
[26 empty] | 0.5 | 0.5
Ramal Godoy Cruz | 2 | [28 empty] | 84668.3453 | 84668.3453 | 84668.3453 | 84668.3453
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Olleros | 3 | [28 empty] | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santa Fe | 1.5 | [34 empty] | 56734.4507 | 56734.4507 | 56734.4507
[36 empty] | 0.5 | 0.5 | 0.5
Ramal Fitz Roy | 0.5 | [37 empty] | 62734.9089
0.5
Ramal Bonpland | 1.5 | [38 empty] | 76457.031 | 76457.031 | 76457.031
[40 empty] | 0.5 | 0.5 | 0.5
Ramal Nicaragua | 1 | [24 empty] | 56046.5514 | 56046.5514
[26 empty] | 0.5 | 0.5
Ramal Costa Rica | 7 | [56 empty] | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Gurruchaga | 1 | [62 empty] | 45149.4816 | 45149.4816
[64 empty] | 0.5 | 0.5
Ramal Armenia | 1 | [65 empty] | 48214.397 | 48214.397
[67 empty] | 0.5 | 0.5
Ramal J. Alvarez | 0.5 | [69 empty] | 117835.6189
0.5
Ramal Lavalleja I | 1.5 | [69 empty] | 73082.7908 | 73082.7908 | 73082.7908
[71 empty] | 0.5 | 0.5 | 0.5
Ramal Cabrera | 1 | [49 empty] | 43239.6469 | 43239.6469
[51 empty] | 0.5 | 0.5
Ramal Niceto Vega Sur | 2 | [49 empty] | 72285.9116 | 72285.9116 | 72285.9116 | 72285.9116
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Niceto Vega Norte | 6 | [54 empty] | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742
[56 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Castillo | 0.5 | [65 empty] | 55621.4443
0.5
Ramal Acevedo | 1.5 | [51 empty] | 68757.9133 | 68757.9133 | 68757.9133
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Lavalleja II | 1 | [51 empty] | 64651.0238 | 64651.0238
[53 empty] | 0.5 | 0.5
Ramal Loyola | 6.5 | [59 empty] | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699
[61 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Velazco | 17 | [38 empty] | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808
[40 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal A. Gallardo | 0.5 | [61 empty] | 59400.5619
0.5
Ramal Lambaré | 1 | [65 empty] | 48647.7295 | 48647.7295
[67 empty] | 0.5 | 0.5
Ramal Estivao | 1 | [67 empty] | 79358.416 | 79358.416
[69 empty] | 0.5 | 0.5
Ramal Vera | 1 | [49 empty] | 46673.1076 | 46673.1076
[51 empty] | 0.5 | 0.5
Ramal Corrientes | 5 | [66 empty] | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707
[68 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Dorrego | 0.5 | [75 empty] | 64033.4167
0.5
Sumideros a Ramales Exist | 19 | [24 empty] | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Murillo | 2 | [68 empty] | 196896.1029 | 196896.1029 | 196896.1029 | 196896.1029
[70 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Muñecas Sur | 1.5 | [66 empty] | 68753.3919 | 68753.3919 | 68753.3919
[68 empty] | 0.5 | 0.5 | 0.5
Ramal Muñecas Norte | 1 | [68 empty] | 84870.5482 | 84870.5482
[70 empty] | 0.5 | 0.5
Ramal Darwin | 1 | [70 empty] | 34080.6876 | 34080.6876
[72 empty] | 0.5 | 0.5
Ramal M. Rosas | 4.5 | [52 empty] | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Caldas | 3 | [61 empty] | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223
[63 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santos Dumont | 1 | [67 empty] | 56626.5552 | 56626.5552
[69 empty] | 0.5 | 0.5
Ramal H. Pueyrredón | 8 | [70 empty] | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Tres Arroyos | 1.5 | [74 empty] | 56762.0448 | 56762.0448 | 56762.0448
[76 empty] | 0.5 | 0.5 | 0.5
Ramal Olaya | 1.5 | [77 empty] | 83417.4807 | 83417.4807 | 83417.4807
[79 empty] | 0.5 | 0.5 | 0.5
Ramal Rojas | 1 | [76 empty] | 39688.4802 | 39688.4802
[78 empty] | 0.5 | 0.5
Ramal Franklin | 1 | [83 empty] | 47703.7952 | 47703.7952
[85 empty] | 0.5 | 0.5
Ramal Arengreen | 5 | [86 empty] | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405
[88 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Aranguren | 1 | [94 empty] | 41661.2822 | 41661.2822
[96 empty] | 0.5 | 0.5
Ramal Cucha Cucha Sur | 2.5 | [50 empty] | 76191.728 | 76191.728 | 76191.728 | 76191.728 | 76191.728
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cucha Cucha Norte | 15.5 | [43 empty] | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Maturín | 1 | [61 empty] | 71493.528 | 71493.528
[63 empty] | 0.5 | 0.5
Ramal Constituyentes | 0.5 | [70 empty] | 38423.8726
0.5
Ramal Paysandú | 1 | [50 empty] | 46136.1796 | 46136.1796
[52 empty] | 0.5 | 0.5
Ramal San Martín | 5.5 | [74 empty] | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795
[76 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Camarones I | 5.5 | [85 empty] | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057
[87 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sánchez | 1 | [88 empty] | 35323.2858 | 35323.2858
[90 empty] | 0.5 | 0.5
Ramal A. Lamas | 1 | [91 empty] | 46983.3613 | 46983.3613
[93 empty] | 0.5 | 0.5
Ramal Seguí | 0.5 | [50 empty] | 77342.6992
0.5
Ramal Mendez de Andés | 5.5 | [49 empty] | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Calcena | 2 | [52 empty] | 59879.5762 | 59879.5762 | 59879.5762 | 59879.5762
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bogotá | 1.5 | [58 empty] | 76937.3008 | 76937.3008 | 76937.3008
[60 empty] | 0.5 | 0.5 | 0.5
Ramal Boyacá Sur | 1 | [52 empty] | 36412.3973 | 36412.3973
[54 empty] | 0.5 | 0.5
Ramal Boyacá Norte | 1.5 | [50 empty] | 50400.3835 | 50400.3835 | 50400.3835
[52 empty] | 0.5 | 0.5 | 0.5
Ramal Caracas | 18 | [60 empty] | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644
[62 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Biarritz | 1.5 | [75 empty] | 71933.6659 | 71933.6659 | 71933.6659
[77 empty] | 0.5 | 0.5 | 0.5
Ramal Carranza | 1 | [78 empty] | 46882.847 | 46882.847
[80 empty] | 0.5 | 0.5
Ramal Santo Tomé I | 0.5 | [84 empty] | 47709.0702
0.5
Ramal Empedrado | 1 | [89 empty] | 95763.2228 | 95763.2228
[91 empty] | 0.5 | 0.5
Ramal Zamudio | 2 | [92 empty] | 140547.3977 | 140547.3977 | 140547.3977 | 140547.3977
[94 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bufano | 1 | [55 empty] | 43875.9928 | 43875.9928
[57 empty] | 0.5 | 0.5
Ramal Bolivia Sur | 1.5 | [59 empty] | 111763.9143 | 111763.9143 | 111763.9143
[61 empty] | 0.5 | 0.5 | 0.5
Ramal Bolivia Norte | 0.5 | [61 empty] | 58219.7546
0.5
Ramal Terrada | 2 | [73 empty] | 63991.8159 | 63991.8159 | 63991.8159 | 63991.8159
[75 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Argerich Sur | 1 | [76 empty] | 48388.6905 | 48388.6905
[78 empty] | 0.5 | 0.5
Ramal Argerich Norte | 8.5 | [48 empty] | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Beláustegui | 1.5 | [51 empty] | 52496.3873 | 52496.3873 | 52496.3873
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Cesar Díaz | 1 | [57 empty] | 38903.9081 | 38903.9081
[59 empty] | 0.5 | 0.5
Ramal Camarones II | 1.5 | [60 empty] | 51716.7099 | 51716.7099 | 51716.7099
[62 empty] | 0.5 | 0.5 | 0.5
Ramal García I | 2 | [65 empty] | 67552.1337 | 67552.1337 | 67552.1337 | 67552.1337
[67 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Campana | 1 | [69 empty] | 42313.5624 | 42313.5624
[71 empty] | 0.5 | 0.5
Ramal Helguera | 1 | [70 empty] | 40587.2993 | 40587.2993
[72 empty] | 0.5 | 0.5
Ramal Galicia | 1.5 | [74 empty] | 44555.9821 | 44555.9821 | 44555.9821
[76 empty] | 0.5 | 0.5 | 0.5
Ramal E. González I | 1.5 | [78 empty] | 55051.6867 | 55051.6867 | 55051.6867
[80 empty] | 0.5 | 0.5 | 0.5
Ramal Vilardebó I | 7 | [50 empty] | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Vilardebó II | 1 | [62 empty] | 38173.1042 | 38173.1042
[64 empty] | 0.5 | 0.5
Ramal Bahía Blanca | 1 | [50 empty] | 61446.7283 | 61446.7283
[52 empty] | 0.5 | 0.5
Ramal E. Lamarca | 0.5 | [66 empty] | 74730.378
0.5
Ramal Chivilcoy | 0.5 | [67 empty] | 100452.7646
0.5
Ramal Sanabria | 1 | [68 empty] | 75715.9069 | 75715.9069
[70 empty] | 0.5 | 0.5
Ramal Segurola | 13 | [70 empty] | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal R. E. De San Martín | 1 | [73 empty] | 53222.1685 | 53222.1685
[75 empty] | 0.5 | 0.5
Ramal E. González II | 1 | [86 empty] | 40335.8049 | 40335.8049
[88 empty] | 0.5 | 0.5
Ramal Santo Tomé II | 1 | [94 empty] | 53780.3587 | 53780.3587
[96 empty] | 0.5 | 0.5
Ramal Goya | 0.5 | [69 empty] | 49125.2383
0.5
Ramal Carrasco | 2.5 | [75 empty] | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774
[77 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez II | 5.5 | [70 empty] | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez I | 3.5 | [81 empty] | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132
[83 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cervantes Sur | 1 | [52 empty] | 63507.7688 | 63507.7688
[54 empty] | 0.5 | 0.5
Ramal Cervantes Norte | 9 | [52 empty] | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Marcos Sastre | 1 | [70 empty] | 71074.5565 | 71074.5565
[72 empty] | 0.5 | 0.5
Ramal Calderón de la Barca | 1 | [50 empty] | 49190.8136 | 49190.8136
[52 empty] | 0.5 | 0.5
Ramal Milton | 1 | [53 empty] | 47806.7739 | 47806.7739
[55 empty] | 0.5 | 0.5
Ramal Virgilio | 1 | [56 empty] | 62504.4586 | 62504.4586
[58 empty] | 0.5 | 0.5
Ramal Victor Hugo | 1 | [59 empty] | 60748.8644 | 60748.8644
[61 empty] | 0.5 | 0.5
Ramal Camarones III | 1 | [62 empty] | 93965.0121 | 93965.0121
[64 empty] | 0.5 | 0.5
Ramal García II | 1 | [65 empty] | 53916.9164 | 53916.9164
[67 empty] | 0.5 | 0.5
Ramal Peralta | 1 | [50 empty] | 49831.2481 | 49831.2481
[52 empty] | 0.5 | 0.5
Ramal Alvarez Jonte | 2 | [52 empty] | 120654.8098 | 120654.8098 | 120654.8098 | 120654.8098
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Barragán | 1 | [56 empty] | 41900.42 | 41900.42
[58 empty] | 0.5 | 0.5
Ramal Cuzco Sur | 6.5 | [83 empty] | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539
[85 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Rivadavia I | 1 | [89 empty] | 84495.646 | 84495.646
[91 empty] | 0.5 | 0.5
Ramal Rivadavia II | 1.5 | [91 empty] | 112932.1063 | 112932.1063 | 112932.1063
[93 empty] | 0.5 | 0.5 | 0.5
Ramal Cuzco Norte | 0.5 | [95 empty] | 70925.8541
0.5
Sumideros a Ramales Exist | 24 | [48 empty] | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25191 | 0.25191 | 0.13785 | 0.13785 | 0.19904 | 0.19904 | 0.19904 | 0.19904 | 0.11437 | 0.11437 | 0.067758 | 0.067758 | 0.067758 | 0.073759 | 0.44642 | 0.59502 | 0.59502 | 0.51856 | 0.51856 | 0.87416 | 1.075 | 1.075 | 1.3679 | 0.9725 | 1.2085 | 1.5466 | 1.8941 | 1.9127 | 2.3726 | 2.233 | 2.1539 | 2.0738 | 2.2079 | 2.203 | 2.1755 | 2.4682 | 2.5906 | 2.6944 | 2.6312 | 2.5597 | 2.1841 | 2.2465 | 2.2808 | 2.1085 | 2.3655 | 2.3756 | 2.5114 | 2.4307 | 1.3502 | 1.4674 | 1.4597 | 1.6199 | 1.5555 | 1.4736 | 1.4156 | 1.4156 | 1.2078 | 1.0224 | 1.0224 | 1.2208 | 1.2685 | 1.181 | 1.1489 | 1.1489 | 1.048 | 1.2283 | 1.193 | 1.1726 | 1.3132 | 1.2662 | 1.2487 | 1.3196
TUNEL | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
Tunel Corto | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251907.2182 | 251907.2182 | 137844.8767 | 137844.8767 | 199034.9041 | 199034.9041 | 199034.9041 | 199034.9041 | 114366.5587 | 114366.5587 | 67757.2741 | 67757.2741 | 67757.2741 | 73757.7323 | 446414.5352 | 595013.206 | 595013.206 | 518556.1749 | 518556.1749 | 664370.0777 | 865187.3192 | 865187.3192 | 1158152.2281 | 762703.2474 | 762703.2474 | 924901.9135 | 663625.428 | 707121.6107 | 707121.6107 | 570184.6753 | 643503.1362 | 643503.1362 | 853771.3893 | 853771.3893 | 853771.3893 | 1012911.6593 | 1012911.6593 | 1072312.2212 | 1047038.3175 | 1098671.5868 | 1053522.1052 | 1206005.676 | 1096766.5282 | 1079262.8178 | 1079262.8178 | 1190822.8114 | 826316.0644 | 826316.0644 | 88458.6707 | 88458.6707 | 88458.6707 | 152492.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 251908.7182 | 251908.7182 | 137845.3767 | 137845.3767 | 199035.9041 | 199035.9041 | 199035.9041 | 199035.9041 | 114367.0587 | 114367.0587 | 67757.7741 | 67757.7741 | 67757.7741 | 73758.2323 | 446415.5352 | 595014.706 | 595014.706 | 518557.1749 | 518557.1749 | 664371.5777 | 865189.8192 | 865189.8192 | 1158155.7281 | 762705.2474 | 762705.2474 | 924905.4135 | 663627.928 | 707124.1107 | 707124.1107 | 570186.1753 | 643504.6362 | 643504.6362 | 853773.3893 | 853773.3893 | 853773.3893 | 1012914.1593 | 1012914.1593 | 1072315.2212 | 1047041.3175 | 1098674.5868 | 1053524.6052 | 1206009.676 | 1096770.0282 | 1079265.8178 | 1079265.8178 | 1190826.3114 | 826318.5644 | 826318.5644 | 88459.1707 | 88459.1707 | 88459.1707 | 152493.0874
Tunel Largo | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 445749.6926 | 621665.8358 | 1230463.8272 | 1205617.5153 | 1665420.3985 | 1662826.7889 | 1510410.2355 | 1430287.7264 | 1354158.219 | 1349186.1344 | 1321718.5566 | 1455327.4271 | 1577653.4582 | 1622045.1942 | 1584199.6417 | 1460989.4038 | 1130593.0764 | 1040504.2599 | 1183988.0298 | 1029202.6329 | 1286232.4263 | 1184739.1462 | 1685078.0406 | 1604340.6056 | 1261701.9593 | 1378915.9437 | 1371249.4259 | 1467438.9007 | 1555516.0714 | 1473623.7094 | 1415547.4064 | 1415547.4064 | 1207769.1013 | 1022351.2297 | 1022351.2297 | 1220793.6788 | 1268502.749 | 1181029.5098 | 1148856.633 | 1148856.633 | 1048020.5007 | 1228279.3695 | 1192956.0837 | 1172612.6824 | 1313160.0802 | 1266176.7189 | 1248686.2535 | 1319612.1076
[45 empty] | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 421347.9907 | 597264.6339 | 1206066.6253 | 1181220.3134 | 1641024.1966 | 1638430.587 | 1486012.5336 | 1405889.5245 | 1329760.0171 | 1324787.9324 | 1297319.8547 | 1430929.2252 | 1553255.7563 | 1597647.4923 | 1559801.9397 | 1436590.7018 | 1106192.8744 | 1016104.558 | 1159589.3279 | 1004803.4309 | 1261834.2244 | 1160340.4442 | 1660680.8386 | 1579942.4037 | 1237301.7573 | 1354516.7417 | 1346851.2239 | 1443041.1988 | 1531119.3695 | 1449226.0075 | 1391149.2045 | 1391149.2045 | 1183369.3994 | 997951.0278 | 997951.0278 | 1196394.4768 | 1244104.047 | 1156629.8078 | 1124457.431 | 1124457.431 | 1023620.7987 | 1203880.6676 | 1168556.8818 | 1148213.4805 | 1288761.3782 | 1241777.5169 | 1224287.5515 | 1295213.9056
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25191 | 0.25191 | 0.13784 | 0.13784 | 0.19903 | 0.19903 | 0.19903 | 0.19903 | 0.11437 | 0.11437 | 0.067757 | 0.067757 | 0.067757 | 0.073758 | 0.44641 | 0.59501 | 0.59501 | 0.51856 | 0.51856 | 0.87416 | 1.075 | 1.075 | 1.3679 | 0.97249 | 1.2085 | 1.5466 | 1.8941 | 1.9127 | 2.3725 | 2.233 | 2.1539 | 2.0738 | 2.2079 | 2.203 | 2.1755 | 2.4682 | 2.5906 | 2.6944 | 2.6312 | 2.5597 | 2.1841 | 2.2465 | 2.2808 | 2.1085 | 2.3655 | 2.3756 | 2.5114 | 2.4307 | 1.3502 | 1.4674 | 1.4597 | 1.6199 | 1.5555 | 1.4736 | 1.4155 | 1.4155 | 1.2078 | 1.0224 | 1.0224 | 1.2208 | 1.2685 | 1.181 | 1.1489 | 1.1489 | 1.048 | 1.2283 | 1.193 | 1.1726 | 1.3132 | 1.2662 | 1.2487 | 1.3196
AGRUPACION DE SECUNDARIOS | GRUPO DE OBRAS
SECUNDARIOS ASOCIADOS AL TUNEL CORTO | A
B
SECUNDARIOS ASOCIADOS AL TUNEL LARGO | C
D
E
F
TOTAL=

## B
SECUNDARIO | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
|  | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5 | 11 | 11.5 | 12 | 12.5 | 13 | 13.5 | 14 | 14.5 | 15 | 15.5 | 16 | 16.5 | 17 | 17.5 | 18 | 18.5 | 19 | 19.5 | 20 | 20.5 | 21 | 21.5 | 22 | 22.5 | 23 | 23.5 | 24 | 24.5 | 25 | 25.5 | 26 | 26.5 | 27 | 27.5 | 28 | 28.5 | 29 | 29.5 | 30 | 30.5 | 31 | 31.5 | 32 | 32.5 | 33 | 33.5 | 34 | 34.5 | 35 | 35.5 | 36 | 36.5 | 37 | 37.5 | 38 | 38.5 | 39 | 39.5 | 40 | 40.5 | 41 | 41.5 | 42 | 42.5 | 43 | 43.5 | 44 | 44.5 | 45 | 45.5 | 46 | 46.5 | 47 | 47.5 | 48 | 48.5
Ramal Lugones | 6 | [44 empty] | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578
[46 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Casares | 3.5 | [56 empty] | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal F. Alcorta | 4.5 | [63 empty] | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521
[65 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Sur | 3.5 | [43 empty] | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Infanta Isabel | 2 | [46 empty] | 115462.5826 | 115462.5826 | 115462.5826 | 115462.5826
[48 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Norte | 0.5 | [46 empty] | 177502.3263
0.5
Ramal Libertador | 4 | [39 empty] | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707
[41 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sinclair | 1.5 | [44 empty] | 69347.9837 | 69347.9837 | 69347.9837
[46 empty] | 0.5 | 0.5 | 0.5
Ramal Arévalo | 2 | [24 empty] | 126822.0533 | 126822.0533 | 126822.0533 | 126822.0533
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Matienzo | 1 | [24 empty] | 58015.7901 | 58015.7901
[26 empty] | 0.5 | 0.5
Ramal Godoy Cruz | 2 | [28 empty] | 84668.3453 | 84668.3453 | 84668.3453 | 84668.3453
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Olleros | 3 | [28 empty] | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santa Fe | 1.5 | [34 empty] | 56734.4507 | 56734.4507 | 56734.4507
[36 empty] | 0.5 | 0.5 | 0.5
Ramal Fitz Roy | 0.5 | [37 empty] | 62734.9089
0.5
Ramal Bonpland | 1.5 | [38 empty] | 76457.031 | 76457.031 | 76457.031
[40 empty] | 0.5 | 0.5 | 0.5
Ramal Nicaragua | 1 | [24 empty] | 56046.5514 | 56046.5514
[26 empty] | 0.5 | 0.5
Ramal Costa Rica | 7 | [56 empty] | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Gurruchaga | 1 | [62 empty] | 45149.4816 | 45149.4816
[64 empty] | 0.5 | 0.5
Ramal Armenia | 1 | [65 empty] | 48214.397 | 48214.397
[67 empty] | 0.5 | 0.5
Ramal J. Alvarez | 0.5 | [69 empty] | 117835.6189
0.5
Ramal Lavalleja I | 1.5 | [69 empty] | 73082.7908 | 73082.7908 | 73082.7908
[71 empty] | 0.5 | 0.5 | 0.5
Ramal Cabrera | 1 | [49 empty] | 43239.6469 | 43239.6469
[51 empty] | 0.5 | 0.5
Ramal Niceto Vega Sur | 2 | [49 empty] | 72285.9116 | 72285.9116 | 72285.9116 | 72285.9116
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Niceto Vega Norte | 6 | [54 empty] | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742
[56 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Castillo | 0.5 | [65 empty] | 55621.4443
0.5
Ramal Acevedo | 1.5 | [51 empty] | 68757.9133 | 68757.9133 | 68757.9133
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Lavalleja II | 1 | [51 empty] | 64651.0238 | 64651.0238
[53 empty] | 0.5 | 0.5
Ramal Loyola | 6.5 | [59 empty] | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699
[61 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Velazco | 17 | [38 empty] | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808
[40 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal A. Gallardo | 0.5 | [61 empty] | 59400.5619
0.5
Ramal Lambaré | 1 | [65 empty] | 48647.7295 | 48647.7295
[67 empty] | 0.5 | 0.5
Ramal Estivao | 1 | [67 empty] | 79358.416 | 79358.416
[69 empty] | 0.5 | 0.5
Ramal Vera | 1 | [49 empty] | 46673.1076 | 46673.1076
[51 empty] | 0.5 | 0.5
Ramal Corrientes | 5 | [66 empty] | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707
[68 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Dorrego | 0.5 | [75 empty] | 64033.4167
0.5
Sumideros a Ramales Exist | 19 | [24 empty] | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Murillo | 2 | [68 empty] | 196896.1029 | 196896.1029 | 196896.1029 | 196896.1029
[70 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Muñecas Sur | 1.5 | [66 empty] | 68753.3919 | 68753.3919 | 68753.3919
[68 empty] | 0.5 | 0.5 | 0.5
Ramal Muñecas Norte | 1 | [68 empty] | 84870.5482 | 84870.5482
[70 empty] | 0.5 | 0.5
Ramal Darwin | 1 | [70 empty] | 34080.6876 | 34080.6876
[72 empty] | 0.5 | 0.5
Ramal M. Rosas | 4.5 | [52 empty] | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Caldas | 3 | [61 empty] | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223
[63 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santos Dumont | 1 | [67 empty] | 56626.5552 | 56626.5552
[69 empty] | 0.5 | 0.5
Ramal H. Pueyrredón | 8 | [70 empty] | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Tres Arroyos | 1.5 | [74 empty] | 56762.0448 | 56762.0448 | 56762.0448
[76 empty] | 0.5 | 0.5 | 0.5
Ramal Olaya | 1.5 | [77 empty] | 83417.4807 | 83417.4807 | 83417.4807
[79 empty] | 0.5 | 0.5 | 0.5
Ramal Rojas | 1 | [76 empty] | 39688.4802 | 39688.4802
[78 empty] | 0.5 | 0.5
Ramal Franklin | 1 | [83 empty] | 47703.7952 | 47703.7952
[85 empty] | 0.5 | 0.5
Ramal Arengreen | 5 | [86 empty] | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405
[88 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Aranguren | 1 | [94 empty] | 41661.2822 | 41661.2822
[96 empty] | 0.5 | 0.5
Ramal Cucha Cucha Sur | 2.5 | [50 empty] | 76191.728 | 76191.728 | 76191.728 | 76191.728 | 76191.728
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cucha Cucha Norte | 15.5 | [43 empty] | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Maturín | 1 | [61 empty] | 71493.528 | 71493.528
[63 empty] | 0.5 | 0.5
Ramal Constituyentes | 0.5 | [70 empty] | 38423.8726
0.5
Ramal Paysandú | 1 | [50 empty] | 46136.1796 | 46136.1796
[52 empty] | 0.5 | 0.5
Ramal San Martín | 5.5 | [74 empty] | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795
[76 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Camarones I | 5.5 | [85 empty] | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057
[87 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sánchez | 1 | [88 empty] | 35323.2858 | 35323.2858
[90 empty] | 0.5 | 0.5
Ramal A. Lamas | 1 | [91 empty] | 46983.3613 | 46983.3613
[93 empty] | 0.5 | 0.5
Ramal Seguí | 0.5 | [50 empty] | 77342.6992
0.5
Ramal Mendez de Andés | 5.5 | [49 empty] | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Calcena | 2 | [52 empty] | 59879.5762 | 59879.5762 | 59879.5762 | 59879.5762
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bogotá | 1.5 | [58 empty] | 76937.3008 | 76937.3008 | 76937.3008
[60 empty] | 0.5 | 0.5 | 0.5
Ramal Boyacá Sur | 1 | [52 empty] | 36412.3973 | 36412.3973
[54 empty] | 0.5 | 0.5
Ramal Boyacá Norte | 1.5 | [50 empty] | 50400.3835 | 50400.3835 | 50400.3835
[52 empty] | 0.5 | 0.5 | 0.5
Ramal Caracas | 18 | [60 empty] | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644
[62 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Biarritz | 1.5 | [75 empty] | 71933.6659 | 71933.6659 | 71933.6659
[77 empty] | 0.5 | 0.5 | 0.5
Ramal Carranza | 1 | [78 empty] | 46882.847 | 46882.847
[80 empty] | 0.5 | 0.5
Ramal Santo Tomé I | 0.5 | [84 empty] | 47709.0702
0.5
Ramal Empedrado | 1 | [89 empty] | 95763.2228 | 95763.2228
[91 empty] | 0.5 | 0.5
Ramal Zamudio | 2 | [92 empty] | 140547.3977 | 140547.3977 | 140547.3977 | 140547.3977
[94 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bufano | 1 | [55 empty] | 43875.9928 | 43875.9928
[57 empty] | 0.5 | 0.5
Ramal Bolivia Sur | 1.5 | [59 empty] | 111763.9143 | 111763.9143 | 111763.9143
[61 empty] | 0.5 | 0.5 | 0.5
Ramal Bolivia Norte | 0.5 | [61 empty] | 58219.7546
0.5
Ramal Terrada | 2 | [73 empty] | 63991.8159 | 63991.8159 | 63991.8159 | 63991.8159
[75 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Argerich Sur | 1 | [76 empty] | 48388.6905 | 48388.6905
[78 empty] | 0.5 | 0.5
Ramal Argerich Norte | 8.5 | [48 empty] | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Beláustegui | 1.5 | [51 empty] | 52496.3873 | 52496.3873 | 52496.3873
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Cesar Díaz | 1 | [57 empty] | 38903.9081 | 38903.9081
[59 empty] | 0.5 | 0.5
Ramal Camarones II | 1.5 | [60 empty] | 51716.7099 | 51716.7099 | 51716.7099
[62 empty] | 0.5 | 0.5 | 0.5
Ramal García I | 2 | [65 empty] | 67552.1337 | 67552.1337 | 67552.1337 | 67552.1337
[67 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Campana | 1 | [69 empty] | 42313.5624 | 42313.5624
[71 empty] | 0.5 | 0.5
Ramal Helguera | 1 | [70 empty] | 40587.2993 | 40587.2993
[72 empty] | 0.5 | 0.5
Ramal Galicia | 1.5 | [74 empty] | 44555.9821 | 44555.9821 | 44555.9821
[76 empty] | 0.5 | 0.5 | 0.5
Ramal E. González I | 1.5 | [78 empty] | 55051.6867 | 55051.6867 | 55051.6867
[80 empty] | 0.5 | 0.5 | 0.5
Ramal Vilardebó I | 7 | [50 empty] | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Vilardebó II | 1 | [62 empty] | 38173.1042 | 38173.1042
[64 empty] | 0.5 | 0.5
Ramal Bahía Blanca | 1 | [50 empty] | 61446.7283 | 61446.7283
[52 empty] | 0.5 | 0.5
Ramal E. Lamarca | 0.5 | [66 empty] | 74730.378
0.5
Ramal Chivilcoy | 0.5 | [67 empty] | 100452.7646
0.5
Ramal Sanabria | 1 | [68 empty] | 75715.9069 | 75715.9069
[70 empty] | 0.5 | 0.5
Ramal Segurola | 13 | [70 empty] | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal R. E. De San Martín | 1 | [73 empty] | 53222.1685 | 53222.1685
[75 empty] | 0.5 | 0.5
Ramal E. González II | 1 | [86 empty] | 40335.8049 | 40335.8049
[88 empty] | 0.5 | 0.5
Ramal Santo Tomé II | 1 | [94 empty] | 53780.3587 | 53780.3587
[96 empty] | 0.5 | 0.5
Ramal Goya | 0.5 | [69 empty] | 49125.2383
0.5
Ramal Carrasco | 2.5 | [75 empty] | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774
[77 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez II | 5.5 | [70 empty] | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez I | 3.5 | [81 empty] | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132
[83 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cervantes Sur | 1 | [52 empty] | 63507.7688 | 63507.7688
[54 empty] | 0.5 | 0.5
Ramal Cervantes Norte | 9 | [52 empty] | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Marcos Sastre | 1 | [70 empty] | 71074.5565 | 71074.5565
[72 empty] | 0.5 | 0.5
Ramal Calderón de la Barca | 1 | [50 empty] | 49190.8136 | 49190.8136
[52 empty] | 0.5 | 0.5
Ramal Milton | 1 | [53 empty] | 47806.7739 | 47806.7739
[55 empty] | 0.5 | 0.5
Ramal Virgilio | 1 | [56 empty] | 62504.4586 | 62504.4586
[58 empty] | 0.5 | 0.5
Ramal Victor Hugo | 1 | [59 empty] | 60748.8644 | 60748.8644
[61 empty] | 0.5 | 0.5
Ramal Camarones III | 1 | [62 empty] | 93965.0121 | 93965.0121
[64 empty] | 0.5 | 0.5
Ramal García II | 1 | [65 empty] | 53916.9164 | 53916.9164
[67 empty] | 0.5 | 0.5
Ramal Peralta | 1 | [50 empty] | 49831.2481 | 49831.2481
[52 empty] | 0.5 | 0.5
Ramal Alvarez Jonte | 2 | [52 empty] | 120654.8098 | 120654.8098 | 120654.8098 | 120654.8098
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Barragán | 1 | [56 empty] | 41900.42 | 41900.42
[58 empty] | 0.5 | 0.5
Ramal Cuzco Sur | 6.5 | [83 empty] | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539
[85 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Rivadavia I | 1 | [89 empty] | 84495.646 | 84495.646
[91 empty] | 0.5 | 0.5
Ramal Rivadavia II | 1.5 | [91 empty] | 112932.1063 | 112932.1063 | 112932.1063
[93 empty] | 0.5 | 0.5 | 0.5
Ramal Cuzco Norte | 0.5 | [95 empty] | 70925.8541
0.5
Sumideros a Ramales Exist | 24 | [48 empty] | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25191 | 0.25191 | 0.13785 | 0.13785 | 0.19904 | 0.19904 | 0.19904 | 0.19904 | 0.11437 | 0.11437 | 0.067758 | 0.067758 | 0.067758 | 0.073759 | 0.44642 | 0.59502 | 0.59502 | 0.51856 | 0.51856 | 0.87416 | 1.075 | 1.075 | 1.3679 | 0.9725 | 1.2085 | 1.5466 | 1.8941 | 1.9127 | 2.3726 | 2.233 | 2.1539 | 2.0738 | 2.2079 | 2.203 | 2.1755 | 2.4682 | 2.5906 | 2.6944 | 2.6312 | 2.5597 | 2.1841 | 2.2465 | 2.2808 | 2.1085 | 2.3655 | 2.3756 | 2.5114 | 2.4307 | 1.3502 | 1.4674 | 1.4597 | 1.6199 | 1.5555 | 1.4736 | 1.4156 | 1.4156 | 1.2078 | 1.0224 | 1.0224 | 1.2208 | 1.2685 | 1.181 | 1.1489 | 1.1489 | 1.048 | 1.2283 | 1.193 | 1.1726 | 1.3132 | 1.2662 | 1.2487 | 1.3196
TUNEL | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
Tunel Corto | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251907.2182 | 251907.2182 | 137844.8767 | 137844.8767 | 199034.9041 | 199034.9041 | 199034.9041 | 199034.9041 | 114366.5587 | 114366.5587 | 67757.2741 | 67757.2741 | 67757.2741 | 73757.7323 | 446414.5352 | 595013.206 | 595013.206 | 518556.1749 | 518556.1749 | 664370.0777 | 865187.3192 | 865187.3192 | 1158152.2281 | 762703.2474 | 762703.2474 | 924901.9135 | 663625.428 | 707121.6107 | 707121.6107 | 570184.6753 | 643503.1362 | 643503.1362 | 853771.3893 | 853771.3893 | 853771.3893 | 1012911.6593 | 1012911.6593 | 1072312.2212 | 1047038.3175 | 1098671.5868 | 1053522.1052 | 1206005.676 | 1096766.5282 | 1079262.8178 | 1079262.8178 | 1190822.8114 | 826316.0644 | 826316.0644 | 88458.6707 | 88458.6707 | 88458.6707 | 152492.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 251908.7182 | 251908.7182 | 137845.3767 | 137845.3767 | 199035.9041 | 199035.9041 | 199035.9041 | 199035.9041 | 114367.0587 | 114367.0587 | 67757.7741 | 67757.7741 | 67757.7741 | 73758.2323 | 446415.5352 | 595014.706 | 595014.706 | 518557.1749 | 518557.1749 | 664371.5777 | 865189.8192 | 865189.8192 | 1158155.7281 | 762705.2474 | 762705.2474 | 924905.4135 | 663627.928 | 707124.1107 | 707124.1107 | 570186.1753 | 643504.6362 | 643504.6362 | 853773.3893 | 853773.3893 | 853773.3893 | 1012914.1593 | 1012914.1593 | 1072315.2212 | 1047041.3175 | 1098674.5868 | 1053524.6052 | 1206009.676 | 1096770.0282 | 1079265.8178 | 1079265.8178 | 1190826.3114 | 826318.5644 | 826318.5644 | 88459.1707 | 88459.1707 | 88459.1707 | 152493.0874
Tunel Largo | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 445749.6926 | 621665.8358 | 1230463.8272 | 1205617.5153 | 1665420.3985 | 1662826.7889 | 1510410.2355 | 1430287.7264 | 1354158.219 | 1349186.1344 | 1321718.5566 | 1455327.4271 | 1577653.4582 | 1622045.1942 | 1584199.6417 | 1460989.4038 | 1130593.0764 | 1040504.2599 | 1183988.0298 | 1029202.6329 | 1286232.4263 | 1184739.1462 | 1685078.0406 | 1604340.6056 | 1261701.9593 | 1378915.9437 | 1371249.4259 | 1467438.9007 | 1555516.0714 | 1473623.7094 | 1415547.4064 | 1415547.4064 | 1207769.1013 | 1022351.2297 | 1022351.2297 | 1220793.6788 | 1268502.749 | 1181029.5098 | 1148856.633 | 1148856.633 | 1048020.5007 | 1228279.3695 | 1192956.0837 | 1172612.6824 | 1313160.0802 | 1266176.7189 | 1248686.2535 | 1319612.1076
[45 empty] | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 421347.9907 | 597264.6339 | 1206066.6253 | 1181220.3134 | 1641024.1966 | 1638430.587 | 1486012.5336 | 1405889.5245 | 1329760.0171 | 1324787.9324 | 1297319.8547 | 1430929.2252 | 1553255.7563 | 1597647.4923 | 1559801.9397 | 1436590.7018 | 1106192.8744 | 1016104.558 | 1159589.3279 | 1004803.4309 | 1261834.2244 | 1160340.4442 | 1660680.8386 | 1579942.4037 | 1237301.7573 | 1354516.7417 | 1346851.2239 | 1443041.1988 | 1531119.3695 | 1449226.0075 | 1391149.2045 | 1391149.2045 | 1183369.3994 | 997951.0278 | 997951.0278 | 1196394.4768 | 1244104.047 | 1156629.8078 | 1124457.431 | 1124457.431 | 1023620.7987 | 1203880.6676 | 1168556.8818 | 1148213.4805 | 1288761.3782 | 1241777.5169 | 1224287.5515 | 1295213.9056
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25191 | 0.25191 | 0.13784 | 0.13784 | 0.19903 | 0.19903 | 0.19903 | 0.19903 | 0.11437 | 0.11437 | 0.067757 | 0.067757 | 0.067757 | 0.073758 | 0.44641 | 0.59501 | 0.59501 | 0.51856 | 0.51856 | 0.87416 | 1.075 | 1.075 | 1.3679 | 0.97249 | 1.2085 | 1.5466 | 1.8941 | 1.9127 | 2.3725 | 2.233 | 2.1539 | 2.0738 | 2.2079 | 2.203 | 2.1755 | 2.4682 | 2.5906 | 2.6944 | 2.6312 | 2.5597 | 2.1841 | 2.2465 | 2.2808 | 2.1085 | 2.3655 | 2.3756 | 2.5114 | 2.4307 | 1.3502 | 1.4674 | 1.4597 | 1.6199 | 1.5555 | 1.4736 | 1.4155 | 1.4155 | 1.2078 | 1.0224 | 1.0224 | 1.2208 | 1.2685 | 1.181 | 1.1489 | 1.1489 | 1.048 | 1.2283 | 1.193 | 1.1726 | 1.3132 | 1.2662 | 1.2487 | 1.3196
AGRUPACION DE SECUNDARIOS | GRUPO DE OBRAS
SECUNDARIOS ASOCIADOS AL TUNEL CORTO | A
B
SECUNDARIOS ASOCIADOS AL TUNEL LARGO | C
D
E
F
TOTAL=

## C
SECUNDARIO | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
|  | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5 | 11 | 11.5 | 12 | 12.5 | 13 | 13.5 | 14 | 14.5 | 15 | 15.5 | 16 | 16.5 | 17 | 17.5 | 18 | 18.5 | 19 | 19.5 | 20 | 20.5 | 21 | 21.5 | 22 | 22.5 | 23 | 23.5 | 24 | 24.5 | 25 | 25.5 | 26 | 26.5 | 27 | 27.5 | 28 | 28.5 | 29 | 29.5 | 30 | 30.5 | 31 | 31.5 | 32 | 32.5 | 33 | 33.5 | 34 | 34.5 | 35 | 35.5 | 36 | 36.5 | 37 | 37.5 | 38 | 38.5 | 39 | 39.5 | 40 | 40.5 | 41 | 41.5 | 42 | 42.5 | 43 | 43.5 | 44 | 44.5 | 45 | 45.5 | 46 | 46.5 | 47 | 47.5 | 48 | 48.5
Ramal Lugones | 6 | [44 empty] | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578
[46 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Casares | 3.5 | [56 empty] | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal F. Alcorta | 4.5 | [63 empty] | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521
[65 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Sur | 3.5 | [43 empty] | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Infanta Isabel | 2 | [46 empty] | 115462.5826 | 115462.5826 | 115462.5826 | 115462.5826
[48 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Norte | 0.5 | [46 empty] | 177502.3263
0.5
Ramal Libertador | 4 | [39 empty] | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707
[41 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sinclair | 1.5 | [44 empty] | 69347.9837 | 69347.9837 | 69347.9837
[46 empty] | 0.5 | 0.5 | 0.5
Ramal Arévalo | 2 | [24 empty] | 126822.0533 | 126822.0533 | 126822.0533 | 126822.0533
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Matienzo | 1 | [24 empty] | 58015.7901 | 58015.7901
[26 empty] | 0.5 | 0.5
Ramal Godoy Cruz | 2 | [28 empty] | 84668.3453 | 84668.3453 | 84668.3453 | 84668.3453
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Olleros | 3 | [28 empty] | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santa Fe | 1.5 | [34 empty] | 56734.4507 | 56734.4507 | 56734.4507
[36 empty] | 0.5 | 0.5 | 0.5
Ramal Fitz Roy | 0.5 | [37 empty] | 62734.9089
0.5
Ramal Bonpland | 1.5 | [38 empty] | 76457.031 | 76457.031 | 76457.031
[40 empty] | 0.5 | 0.5 | 0.5
Ramal Nicaragua | 1 | [24 empty] | 56046.5514 | 56046.5514
[26 empty] | 0.5 | 0.5
Ramal Costa Rica | 7 | [56 empty] | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Gurruchaga | 1 | [62 empty] | 45149.4816 | 45149.4816
[64 empty] | 0.5 | 0.5
Ramal Armenia | 1 | [65 empty] | 48214.397 | 48214.397
[67 empty] | 0.5 | 0.5
Ramal J. Alvarez | 0.5 | [69 empty] | 117835.6189
0.5
Ramal Lavalleja I | 1.5 | [69 empty] | 73082.7908 | 73082.7908 | 73082.7908
[71 empty] | 0.5 | 0.5 | 0.5
Ramal Cabrera | 1 | [49 empty] | 43239.6469 | 43239.6469
[51 empty] | 0.5 | 0.5
Ramal Niceto Vega Sur | 2 | [49 empty] | 72285.9116 | 72285.9116 | 72285.9116 | 72285.9116
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Niceto Vega Norte | 6 | [54 empty] | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742
[56 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Castillo | 0.5 | [65 empty] | 55621.4443
0.5
Ramal Acevedo | 1.5 | [51 empty] | 68757.9133 | 68757.9133 | 68757.9133
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Lavalleja II | 1 | [51 empty] | 64651.0238 | 64651.0238
[53 empty] | 0.5 | 0.5
Ramal Loyola | 6.5 | [59 empty] | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699
[61 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Velazco | 17 | [38 empty] | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808
[40 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal A. Gallardo | 0.5 | [61 empty] | 59400.5619
0.5
Ramal Lambaré | 1 | [65 empty] | 48647.7295 | 48647.7295
[67 empty] | 0.5 | 0.5
Ramal Estivao | 1 | [67 empty] | 79358.416 | 79358.416
[69 empty] | 0.5 | 0.5
Ramal Vera | 1 | [49 empty] | 46673.1076 | 46673.1076
[51 empty] | 0.5 | 0.5
Ramal Corrientes | 5 | [66 empty] | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707
[68 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Dorrego | 0.5 | [75 empty] | 64033.4167
0.5
Sumideros a Ramales Exist | 19 | [24 empty] | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Murillo | 2 | [68 empty] | 196896.1029 | 196896.1029 | 196896.1029 | 196896.1029
[70 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Muñecas Sur | 1.5 | [66 empty] | 68753.3919 | 68753.3919 | 68753.3919
[68 empty] | 0.5 | 0.5 | 0.5
Ramal Muñecas Norte | 1 | [68 empty] | 84870.5482 | 84870.5482
[70 empty] | 0.5 | 0.5
Ramal Darwin | 1 | [70 empty] | 34080.6876 | 34080.6876
[72 empty] | 0.5 | 0.5
Ramal M. Rosas | 4.5 | [52 empty] | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Caldas | 3 | [61 empty] | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223
[63 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santos Dumont | 1 | [67 empty] | 56626.5552 | 56626.5552
[69 empty] | 0.5 | 0.5
Ramal H. Pueyrredón | 8 | [70 empty] | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Tres Arroyos | 1.5 | [74 empty] | 56762.0448 | 56762.0448 | 56762.0448
[76 empty] | 0.5 | 0.5 | 0.5
Ramal Olaya | 1.5 | [77 empty] | 83417.4807 | 83417.4807 | 83417.4807
[79 empty] | 0.5 | 0.5 | 0.5
Ramal Rojas | 1 | [76 empty] | 39688.4802 | 39688.4802
[78 empty] | 0.5 | 0.5
Ramal Franklin | 1 | [83 empty] | 47703.7952 | 47703.7952
[85 empty] | 0.5 | 0.5
Ramal Arengreen | 5 | [86 empty] | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405
[88 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Aranguren | 1 | [94 empty] | 41661.2822 | 41661.2822
[96 empty] | 0.5 | 0.5
Ramal Cucha Cucha Sur | 2.5 | [50 empty] | 76191.728 | 76191.728 | 76191.728 | 76191.728 | 76191.728
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cucha Cucha Norte | 15.5 | [43 empty] | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Maturín | 1 | [61 empty] | 71493.528 | 71493.528
[63 empty] | 0.5 | 0.5
Ramal Constituyentes | 0.5 | [70 empty] | 38423.8726
0.5
Ramal Paysandú | 1 | [50 empty] | 46136.1796 | 46136.1796
[52 empty] | 0.5 | 0.5
Ramal San Martín | 5.5 | [74 empty] | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795
[76 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Camarones I | 5.5 | [85 empty] | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057
[87 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sánchez | 1 | [88 empty] | 35323.2858 | 35323.2858
[90 empty] | 0.5 | 0.5
Ramal A. Lamas | 1 | [91 empty] | 46983.3613 | 46983.3613
[93 empty] | 0.5 | 0.5
Ramal Seguí | 0.5 | [50 empty] | 77342.6992
0.5
Ramal Mendez de Andés | 5.5 | [49 empty] | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Calcena | 2 | [52 empty] | 59879.5762 | 59879.5762 | 59879.5762 | 59879.5762
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bogotá | 1.5 | [58 empty] | 76937.3008 | 76937.3008 | 76937.3008
[60 empty] | 0.5 | 0.5 | 0.5
Ramal Boyacá Sur | 1 | [52 empty] | 36412.3973 | 36412.3973
[54 empty] | 0.5 | 0.5
Ramal Boyacá Norte | 1.5 | [50 empty] | 50400.3835 | 50400.3835 | 50400.3835
[52 empty] | 0.5 | 0.5 | 0.5
Ramal Caracas | 18 | [60 empty] | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644
[62 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Biarritz | 1.5 | [75 empty] | 71933.6659 | 71933.6659 | 71933.6659
[77 empty] | 0.5 | 0.5 | 0.5
Ramal Carranza | 1 | [78 empty] | 46882.847 | 46882.847
[80 empty] | 0.5 | 0.5
Ramal Santo Tomé I | 0.5 | [84 empty] | 47709.0702
0.5
Ramal Empedrado | 1 | [89 empty] | 95763.2228 | 95763.2228
[91 empty] | 0.5 | 0.5
Ramal Zamudio | 2 | [92 empty] | 140547.3977 | 140547.3977 | 140547.3977 | 140547.3977
[94 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bufano | 1 | [55 empty] | 43875.9928 | 43875.9928
[57 empty] | 0.5 | 0.5
Ramal Bolivia Sur | 1.5 | [59 empty] | 111763.9143 | 111763.9143 | 111763.9143
[61 empty] | 0.5 | 0.5 | 0.5
Ramal Bolivia Norte | 0.5 | [61 empty] | 58219.7546
0.5
Ramal Terrada | 2 | [73 empty] | 63991.8159 | 63991.8159 | 63991.8159 | 63991.8159
[75 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Argerich Sur | 1 | [76 empty] | 48388.6905 | 48388.6905
[78 empty] | 0.5 | 0.5
Ramal Argerich Norte | 8.5 | [48 empty] | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Beláustegui | 1.5 | [51 empty] | 52496.3873 | 52496.3873 | 52496.3873
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Cesar Díaz | 1 | [57 empty] | 38903.9081 | 38903.9081
[59 empty] | 0.5 | 0.5
Ramal Camarones II | 1.5 | [60 empty] | 51716.7099 | 51716.7099 | 51716.7099
[62 empty] | 0.5 | 0.5 | 0.5
Ramal García I | 2 | [65 empty] | 67552.1337 | 67552.1337 | 67552.1337 | 67552.1337
[67 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Campana | 1 | [69 empty] | 42313.5624 | 42313.5624
[71 empty] | 0.5 | 0.5
Ramal Helguera | 1 | [70 empty] | 40587.2993 | 40587.2993
[72 empty] | 0.5 | 0.5
Ramal Galicia | 1.5 | [74 empty] | 44555.9821 | 44555.9821 | 44555.9821
[76 empty] | 0.5 | 0.5 | 0.5
Ramal E. González I | 1.5 | [78 empty] | 55051.6867 | 55051.6867 | 55051.6867
[80 empty] | 0.5 | 0.5 | 0.5
Ramal Vilardebó I | 7 | [50 empty] | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Vilardebó II | 1 | [62 empty] | 38173.1042 | 38173.1042
[64 empty] | 0.5 | 0.5
Ramal Bahía Blanca | 1 | [50 empty] | 61446.7283 | 61446.7283
[52 empty] | 0.5 | 0.5
Ramal E. Lamarca | 0.5 | [66 empty] | 74730.378
0.5
Ramal Chivilcoy | 0.5 | [67 empty] | 100452.7646
0.5
Ramal Sanabria | 1 | [68 empty] | 75715.9069 | 75715.9069
[70 empty] | 0.5 | 0.5
Ramal Segurola | 13 | [70 empty] | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal R. E. De San Martín | 1 | [73 empty] | 53222.1685 | 53222.1685
[75 empty] | 0.5 | 0.5
Ramal E. González II | 1 | [86 empty] | 40335.8049 | 40335.8049
[88 empty] | 0.5 | 0.5
Ramal Santo Tomé II | 1 | [94 empty] | 53780.3587 | 53780.3587
[96 empty] | 0.5 | 0.5
Ramal Goya | 0.5 | [69 empty] | 49125.2383
0.5
Ramal Carrasco | 2.5 | [75 empty] | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774
[77 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez II | 5.5 | [70 empty] | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez I | 3.5 | [81 empty] | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132
[83 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cervantes Sur | 1 | [52 empty] | 63507.7688 | 63507.7688
[54 empty] | 0.5 | 0.5
Ramal Cervantes Norte | 9 | [52 empty] | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Marcos Sastre | 1 | [70 empty] | 71074.5565 | 71074.5565
[72 empty] | 0.5 | 0.5
Ramal Calderón de la Barca | 1 | [50 empty] | 49190.8136 | 49190.8136
[52 empty] | 0.5 | 0.5
Ramal Milton | 1 | [53 empty] | 47806.7739 | 47806.7739
[55 empty] | 0.5 | 0.5
Ramal Virgilio | 1 | [56 empty] | 62504.4586 | 62504.4586
[58 empty] | 0.5 | 0.5
Ramal Victor Hugo | 1 | [59 empty] | 60748.8644 | 60748.8644
[61 empty] | 0.5 | 0.5
Ramal Camarones III | 1 | [62 empty] | 93965.0121 | 93965.0121
[64 empty] | 0.5 | 0.5
Ramal García II | 1 | [65 empty] | 53916.9164 | 53916.9164
[67 empty] | 0.5 | 0.5
Ramal Peralta | 1 | [50 empty] | 49831.2481 | 49831.2481
[52 empty] | 0.5 | 0.5
Ramal Alvarez Jonte | 2 | [52 empty] | 120654.8098 | 120654.8098 | 120654.8098 | 120654.8098
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Barragán | 1 | [56 empty] | 41900.42 | 41900.42
[58 empty] | 0.5 | 0.5
Ramal Cuzco Sur | 6.5 | [83 empty] | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539
[85 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Rivadavia I | 1 | [89 empty] | 84495.646 | 84495.646
[91 empty] | 0.5 | 0.5
Ramal Rivadavia II | 1.5 | [91 empty] | 112932.1063 | 112932.1063 | 112932.1063
[93 empty] | 0.5 | 0.5 | 0.5
Ramal Cuzco Norte | 0.5 | [95 empty] | 70925.8541
0.5
Sumideros a Ramales Exist | 24 | [48 empty] | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
TUNEL | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
Tunel Corto | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251907.2182 | 251907.2182 | 137844.8767 | 137844.8767 | 199034.9041 | 199034.9041 | 199034.9041 | 199034.9041 | 114366.5587 | 114366.5587 | 67757.2741 | 67757.2741 | 67757.2741 | 73757.7323 | 446414.5352 | 595013.206 | 595013.206 | 518556.1749 | 518556.1749 | 664370.0777 | 865187.3192 | 865187.3192 | 1158152.2281 | 762703.2474 | 762703.2474 | 924901.9135 | 663625.428 | 707121.6107 | 707121.6107 | 570184.6753 | 643503.1362 | 643503.1362 | 853771.3893 | 853771.3893 | 853771.3893 | 1012911.6593 | 1012911.6593 | 1072312.2212 | 1047038.3175 | 1098671.5868 | 1053522.1052 | 1206005.676 | 1096766.5282 | 1079262.8178 | 1079262.8178 | 1190822.8114 | 826316.0644 | 826316.0644 | 88458.6707 | 88458.6707 | 88458.6707 | 152492.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 251908.7182 | 251908.7182 | 137845.3767 | 137845.3767 | 199035.9041 | 199035.9041 | 199035.9041 | 199035.9041 | 114367.0587 | 114367.0587 | 67757.7741 | 67757.7741 | 67757.7741 | 73758.2323 | 446415.5352 | 595014.706 | 595014.706 | 518557.1749 | 518557.1749 | 664371.5777 | 865189.8192 | 865189.8192 | 1158155.7281 | 762705.2474 | 762705.2474 | 924905.4135 | 663627.928 | 707124.1107 | 707124.1107 | 570186.1753 | 643504.6362 | 643504.6362 | 853773.3893 | 853773.3893 | 853773.3893 | 1012914.1593 | 1012914.1593 | 1072315.2212 | 1047041.3175 | 1098674.5868 | 1053524.6052 | 1206009.676 | 1096770.0282 | 1079265.8178 | 1079265.8178 | 1190826.3114 | 826318.5644 | 826318.5644 | 88459.1707 | 88459.1707 | 88459.1707 | 152493.0874
Tunel Largo | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 445749.6926 | 621665.8358 | 1230463.8272 | 1205617.5153 | 1665420.3985 | 1662826.7889 | 1510410.2355 | 1430287.7264 | 1354158.219 | 1349186.1344 | 1321718.5566 | 1455327.4271 | 1577653.4582 | 1622045.1942 | 1584199.6417 | 1460989.4038 | 1130593.0764 | 1040504.2599 | 1183988.0298 | 1029202.6329 | 1286232.4263 | 1184739.1462 | 1685078.0406 | 1604340.6056 | 1261701.9593 | 1378915.9437 | 1371249.4259 | 1467438.9007 | 1555516.0714 | 1473623.7094 | 1415547.4064 | 1415547.4064 | 1207769.1013 | 1022351.2297 | 1022351.2297 | 1220793.6788 | 1268502.749 | 1181029.5098 | 1148856.633 | 1148856.633 | 1048020.5007 | 1228279.3695 | 1192956.0837 | 1172612.6824 | 1313160.0802 | 1266176.7189 | 1248686.2535 | 1319612.1076
[45 empty] | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 421347.9907 | 597264.6339 | 1206066.6253 | 1181220.3134 | 1641024.1966 | 1638430.587 | 1486012.5336 | 1405889.5245 | 1329760.0171 | 1324787.9324 | 1297319.8547 | 1430929.2252 | 1553255.7563 | 1597647.4923 | 1559801.9397 | 1436590.7018 | 1106192.8744 | 1016104.558 | 1159589.3279 | 1004803.4309 | 1261834.2244 | 1160340.4442 | 1660680.8386 | 1579942.4037 | 1237301.7573 | 1354516.7417 | 1346851.2239 | 1443041.1988 | 1531119.3695 | 1449226.0075 | 1391149.2045 | 1391149.2045 | 1183369.3994 | 997951.0278 | 997951.0278 | 1196394.4768 | 1244104.047 | 1156629.8078 | 1124457.431 | 1124457.431 | 1023620.7987 | 1203880.6676 | 1168556.8818 | 1148213.4805 | 1288761.3782 | 1241777.5169 | 1224287.5515 | 1295213.9056
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25191 | 0.25191 | 0.13784 | 0.13784 | 0.19903 | 0.19903 | 0.19903 | 0.19903 | 0.11437 | 0.11437 | 0.067757 | 0.067757 | 0.067757 | 0.073758 | 0.44641 | 0.59501 | 0.59501 | 0.51856 | 0.51856 | 0.87416 | 1.075 | 1.075 | 1.3679 | 0.97249 | 1.2085 | 1.5466 | 1.8941 | 1.9127 | 2.3725 | 2.233 | 2.1539 | 2.0738 | 2.2079 | 2.203 | 2.1755 | 2.4682 | 2.5906 | 2.6944 | 2.6312 | 2.5597 | 2.1841 | 2.2465 | 2.2808 | 2.1085 | 2.3655 | 2.3756 | 2.5114 | 2.4307 | 1.3502 | 1.4674 | 1.4597 | 1.6199 | 1.5555 | 1.4736 | 1.4155 | 1.4155 | 1.2078 | 1.0224 | 1.0224 | 1.2208 | 1.2685 | 1.181 | 1.1489 | 1.1489 | 1.048 | 1.2283 | 1.193 | 1.1726 | 1.3132 | 1.2662 | 1.2487 | 1.3196 | 94315426.599

## D
SECUNDARIO | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
|  | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5 | 11 | 11.5 | 12 | 12.5 | 13 | 13.5 | 14 | 14.5 | 15 | 15.5 | 16 | 16.5 | 17 | 17.5 | 18 | 18.5 | 19 | 19.5 | 20 | 20.5 | 21 | 21.5 | 22 | 22.5 | 23 | 23.5 | 24 | 24.5 | 25 | 25.5 | 26 | 26.5 | 27 | 27.5 | 28 | 28.5 | 29 | 29.5 | 30 | 30.5 | 31 | 31.5 | 32 | 32.5 | 33 | 33.5 | 34 | 34.5 | 35 | 35.5 | 36 | 36.5 | 37 | 37.5 | 38 | 38.5 | 39 | 39.5 | 40 | 40.5 | 41 | 41.5 | 42 | 42.5 | 43 | 43.5 | 44 | 44.5 | 45 | 45.5 | 46 | 46.5 | 47 | 47.5 | 48 | 48.5
Ramal Lugones | 6 | [44 empty] | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578
[46 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Casares | 3.5 | [56 empty] | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal F. Alcorta | 4.5 | [63 empty] | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521
[65 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Sur | 3.5 | [43 empty] | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Infanta Isabel | 2 | [46 empty] | 115462.5826 | 115462.5826 | 115462.5826 | 115462.5826
[48 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Norte | 0.5 | [46 empty] | 177502.3263
0.5
Ramal Libertador | 4 | [39 empty] | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707
[41 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sinclair | 1.5 | [44 empty] | 69347.9837 | 69347.9837 | 69347.9837
[46 empty] | 0.5 | 0.5 | 0.5
Ramal Arévalo | 2 | [24 empty] | 126822.0533 | 126822.0533 | 126822.0533 | 126822.0533
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Matienzo | 1 | [24 empty] | 58015.7901 | 58015.7901
[26 empty] | 0.5 | 0.5
Ramal Godoy Cruz | 2 | [28 empty] | 84668.3453 | 84668.3453 | 84668.3453 | 84668.3453
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Olleros | 3 | [28 empty] | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santa Fe | 1.5 | [34 empty] | 56734.4507 | 56734.4507 | 56734.4507
[36 empty] | 0.5 | 0.5 | 0.5
Ramal Fitz Roy | 0.5 | [37 empty] | 62734.9089
0.5
Ramal Bonpland | 1.5 | [38 empty] | 76457.031 | 76457.031 | 76457.031
[40 empty] | 0.5 | 0.5 | 0.5
Ramal Nicaragua | 1 | [24 empty] | 56046.5514 | 56046.5514
[26 empty] | 0.5 | 0.5
Ramal Costa Rica | 7 | [56 empty] | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Gurruchaga | 1 | [62 empty] | 45149.4816 | 45149.4816
[64 empty] | 0.5 | 0.5
Ramal Armenia | 1 | [65 empty] | 48214.397 | 48214.397
[67 empty] | 0.5 | 0.5
Ramal J. Alvarez | 0.5 | [69 empty] | 117835.6189
0.5
Ramal Lavalleja I | 1.5 | [69 empty] | 73082.7908 | 73082.7908 | 73082.7908
[71 empty] | 0.5 | 0.5 | 0.5
Ramal Cabrera | 1 | [49 empty] | 43239.6469 | 43239.6469
[51 empty] | 0.5 | 0.5
Ramal Niceto Vega Sur | 2 | [49 empty] | 72285.9116 | 72285.9116 | 72285.9116 | 72285.9116
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Niceto Vega Norte | 6 | [54 empty] | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742
[56 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Castillo | 0.5 | [65 empty] | 55621.4443
0.5
Ramal Acevedo | 1.5 | [51 empty] | 68757.9133 | 68757.9133 | 68757.9133
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Lavalleja II | 1 | [51 empty] | 64651.0238 | 64651.0238
[53 empty] | 0.5 | 0.5
Ramal Loyola | 6.5 | [59 empty] | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699
[61 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Velazco | 17 | [38 empty] | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808
[40 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal A. Gallardo | 0.5 | [61 empty] | 59400.5619
0.5
Ramal Lambaré | 1 | [65 empty] | 48647.7295 | 48647.7295
[67 empty] | 0.5 | 0.5
Ramal Estivao | 1 | [67 empty] | 79358.416 | 79358.416
[69 empty] | 0.5 | 0.5
Ramal Vera | 1 | [49 empty] | 46673.1076 | 46673.1076
[51 empty] | 0.5 | 0.5
Ramal Corrientes | 5 | [66 empty] | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707
[68 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Dorrego | 0.5 | [75 empty] | 64033.4167
0.5
Sumideros a Ramales Exist | 19 | [24 empty] | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Murillo | 2 | [68 empty] | 196896.1029 | 196896.1029 | 196896.1029 | 196896.1029
[70 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Muñecas Sur | 1.5 | [66 empty] | 68753.3919 | 68753.3919 | 68753.3919
[68 empty] | 0.5 | 0.5 | 0.5
Ramal Muñecas Norte | 1 | [68 empty] | 84870.5482 | 84870.5482
[70 empty] | 0.5 | 0.5
Ramal Darwin | 1 | [70 empty] | 34080.6876 | 34080.6876
[72 empty] | 0.5 | 0.5
Ramal M. Rosas | 4.5 | [52 empty] | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Caldas | 3 | [61 empty] | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223
[63 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santos Dumont | 1 | [67 empty] | 56626.5552 | 56626.5552
[69 empty] | 0.5 | 0.5
Ramal H. Pueyrredón | 8 | [70 empty] | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Tres Arroyos | 1.5 | [74 empty] | 56762.0448 | 56762.0448 | 56762.0448
[76 empty] | 0.5 | 0.5 | 0.5
Ramal Olaya | 1.5 | [77 empty] | 83417.4807 | 83417.4807 | 83417.4807
[79 empty] | 0.5 | 0.5 | 0.5
Ramal Rojas | 1 | [76 empty] | 39688.4802 | 39688.4802
[78 empty] | 0.5 | 0.5
Ramal Franklin | 1 | [83 empty] | 47703.7952 | 47703.7952
[85 empty] | 0.5 | 0.5
Ramal Arengreen | 5 | [86 empty] | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405
[88 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Aranguren | 1 | [94 empty] | 41661.2822 | 41661.2822
[96 empty] | 0.5 | 0.5
Ramal Cucha Cucha Sur | 2.5 | [50 empty] | 76191.728 | 76191.728 | 76191.728 | 76191.728 | 76191.728
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cucha Cucha Norte | 15.5 | [43 empty] | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Maturín | 1 | [61 empty] | 71493.528 | 71493.528
[63 empty] | 0.5 | 0.5
Ramal Constituyentes | 0.5 | [70 empty] | 38423.8726
0.5
Ramal Paysandú | 1 | [50 empty] | 46136.1796 | 46136.1796
[52 empty] | 0.5 | 0.5
Ramal San Martín | 5.5 | [74 empty] | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795
[76 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Camarones I | 5.5 | [85 empty] | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057
[87 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sánchez | 1 | [88 empty] | 35323.2858 | 35323.2858
[90 empty] | 0.5 | 0.5
Ramal A. Lamas | 1 | [91 empty] | 46983.3613 | 46983.3613
[93 empty] | 0.5 | 0.5
Ramal Seguí | 0.5 | [50 empty] | 77342.6992
0.5
Ramal Mendez de Andés | 5.5 | [49 empty] | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Calcena | 2 | [52 empty] | 59879.5762 | 59879.5762 | 59879.5762 | 59879.5762
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bogotá | 1.5 | [58 empty] | 76937.3008 | 76937.3008 | 76937.3008
[60 empty] | 0.5 | 0.5 | 0.5
Ramal Boyacá Sur | 1 | [52 empty] | 36412.3973 | 36412.3973
[54 empty] | 0.5 | 0.5
Ramal Boyacá Norte | 1.5 | [50 empty] | 50400.3835 | 50400.3835 | 50400.3835
[52 empty] | 0.5 | 0.5 | 0.5
Ramal Caracas | 18 | [60 empty] | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644
[62 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Biarritz | 1.5 | [75 empty] | 71933.6659 | 71933.6659 | 71933.6659
[77 empty] | 0.5 | 0.5 | 0.5
Ramal Carranza | 1 | [78 empty] | 46882.847 | 46882.847
[80 empty] | 0.5 | 0.5
Ramal Santo Tomé I | 0.5 | [84 empty] | 47709.0702
0.5
Ramal Empedrado | 1 | [89 empty] | 95763.2228 | 95763.2228
[91 empty] | 0.5 | 0.5
Ramal Zamudio | 2 | [92 empty] | 140547.3977 | 140547.3977 | 140547.3977 | 140547.3977
[94 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bufano | 1 | [55 empty] | 43875.9928 | 43875.9928
[57 empty] | 0.5 | 0.5
Ramal Bolivia Sur | 1.5 | [59 empty] | 111763.9143 | 111763.9143 | 111763.9143
[61 empty] | 0.5 | 0.5 | 0.5
Ramal Bolivia Norte | 0.5 | [61 empty] | 58219.7546
0.5
Ramal Terrada | 2 | [73 empty] | 63991.8159 | 63991.8159 | 63991.8159 | 63991.8159
[75 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Argerich Sur | 1 | [76 empty] | 48388.6905 | 48388.6905
[78 empty] | 0.5 | 0.5
Ramal Argerich Norte | 8.5 | [48 empty] | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Beláustegui | 1.5 | [51 empty] | 52496.3873 | 52496.3873 | 52496.3873
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Cesar Díaz | 1 | [57 empty] | 38903.9081 | 38903.9081
[59 empty] | 0.5 | 0.5
Ramal Camarones II | 1.5 | [60 empty] | 51716.7099 | 51716.7099 | 51716.7099
[62 empty] | 0.5 | 0.5 | 0.5
Ramal García I | 2 | [65 empty] | 67552.1337 | 67552.1337 | 67552.1337 | 67552.1337
[67 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Campana | 1 | [69 empty] | 42313.5624 | 42313.5624
[71 empty] | 0.5 | 0.5
Ramal Helguera | 1 | [70 empty] | 40587.2993 | 40587.2993
[72 empty] | 0.5 | 0.5
Ramal Galicia | 1.5 | [74 empty] | 44555.9821 | 44555.9821 | 44555.9821
[76 empty] | 0.5 | 0.5 | 0.5
Ramal E. González I | 1.5 | [78 empty] | 55051.6867 | 55051.6867 | 55051.6867
[80 empty] | 0.5 | 0.5 | 0.5
Ramal Vilardebó I | 7 | [50 empty] | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Vilardebó II | 1 | [62 empty] | 38173.1042 | 38173.1042
[64 empty] | 0.5 | 0.5
Ramal Bahía Blanca | 1 | [50 empty] | 61446.7283 | 61446.7283
[52 empty] | 0.5 | 0.5
Ramal E. Lamarca | 0.5 | [66 empty] | 74730.378
0.5
Ramal Chivilcoy | 0.5 | [67 empty] | 100452.7646
0.5
Ramal Sanabria | 1 | [68 empty] | 75715.9069 | 75715.9069
[70 empty] | 0.5 | 0.5
Ramal Segurola | 13 | [70 empty] | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal R. E. De San Martín | 1 | [73 empty] | 53222.1685 | 53222.1685
[75 empty] | 0.5 | 0.5
Ramal E. González II | 1 | [86 empty] | 40335.8049 | 40335.8049
[88 empty] | 0.5 | 0.5
Ramal Santo Tomé II | 1 | [94 empty] | 53780.3587 | 53780.3587
[96 empty] | 0.5 | 0.5
Ramal Goya | 0.5 | [69 empty] | 49125.2383
0.5
Ramal Carrasco | 2.5 | [75 empty] | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774
[77 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez II | 5.5 | [70 empty] | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez I | 3.5 | [81 empty] | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132
[83 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cervantes Sur | 1 | [52 empty] | 63507.7688 | 63507.7688
[54 empty] | 0.5 | 0.5
Ramal Cervantes Norte | 9 | [52 empty] | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Marcos Sastre | 1 | [70 empty] | 71074.5565 | 71074.5565
[72 empty] | 0.5 | 0.5
Ramal Calderón de la Barca | 1 | [50 empty] | 49190.8136 | 49190.8136
[52 empty] | 0.5 | 0.5
Ramal Milton | 1 | [53 empty] | 47806.7739 | 47806.7739
[55 empty] | 0.5 | 0.5
Ramal Virgilio | 1 | [56 empty] | 62504.4586 | 62504.4586
[58 empty] | 0.5 | 0.5
Ramal Victor Hugo | 1 | [59 empty] | 60748.8644 | 60748.8644
[61 empty] | 0.5 | 0.5
Ramal Camarones III | 1 | [62 empty] | 93965.0121 | 93965.0121
[64 empty] | 0.5 | 0.5
Ramal García II | 1 | [65 empty] | 53916.9164 | 53916.9164
[67 empty] | 0.5 | 0.5
Ramal Peralta | 1 | [50 empty] | 49831.2481 | 49831.2481
[52 empty] | 0.5 | 0.5
Ramal Alvarez Jonte | 2 | [52 empty] | 120654.8098 | 120654.8098 | 120654.8098 | 120654.8098
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Barragán | 1 | [56 empty] | 41900.42 | 41900.42
[58 empty] | 0.5 | 0.5
Ramal Cuzco Sur | 6.5 | [83 empty] | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539
[85 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Rivadavia I | 1 | [89 empty] | 84495.646 | 84495.646
[91 empty] | 0.5 | 0.5
Ramal Rivadavia II | 1.5 | [91 empty] | 112932.1063 | 112932.1063 | 112932.1063
[93 empty] | 0.5 | 0.5 | 0.5
Ramal Cuzco Norte | 0.5 | [95 empty] | 70925.8541
0.5
Sumideros a Ramales Exist | 24 | [48 empty] | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25191 | 0.25191 | 0.13785 | 0.13785 | 0.19904 | 0.19904 | 0.19904 | 0.19904 | 0.11437 | 0.11437 | 0.067758 | 0.067758 | 0.067758 | 0.073759 | 0.44642 | 0.59502 | 0.59502 | 0.51856 | 0.51856 | 0.87416 | 1.075 | 1.075 | 1.3679 | 0.9725 | 1.2085 | 1.5466 | 1.8941 | 1.9127 | 2.3726 | 2.233 | 2.1539 | 2.0738 | 2.2079 | 2.203 | 2.1755 | 2.4682 | 2.5906 | 2.6944 | 2.6312 | 2.5597 | 2.1841 | 2.2465 | 2.2808 | 2.1085 | 2.3655 | 2.3756 | 2.5114 | 2.4307 | 1.3502 | 1.4674 | 1.4597 | 1.6199 | 1.5555 | 1.4736 | 1.4156 | 1.4156 | 1.2078 | 1.0224 | 1.0224 | 1.2208 | 1.2685 | 1.181 | 1.1489 | 1.1489 | 1.048 | 1.2283 | 1.193 | 1.1726 | 1.3132 | 1.2662 | 1.2487 | 1.3196
TUNEL | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
Tunel Corto | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251907.2182 | 251907.2182 | 137844.8767 | 137844.8767 | 199034.9041 | 199034.9041 | 199034.9041 | 199034.9041 | 114366.5587 | 114366.5587 | 67757.2741 | 67757.2741 | 67757.2741 | 73757.7323 | 446414.5352 | 595013.206 | 595013.206 | 518556.1749 | 518556.1749 | 664370.0777 | 865187.3192 | 865187.3192 | 1158152.2281 | 762703.2474 | 762703.2474 | 924901.9135 | 663625.428 | 707121.6107 | 707121.6107 | 570184.6753 | 643503.1362 | 643503.1362 | 853771.3893 | 853771.3893 | 853771.3893 | 1012911.6593 | 1012911.6593 | 1072312.2212 | 1047038.3175 | 1098671.5868 | 1053522.1052 | 1206005.676 | 1096766.5282 | 1079262.8178 | 1079262.8178 | 1190822.8114 | 826316.0644 | 826316.0644 | 88458.6707 | 88458.6707 | 88458.6707 | 152492.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 251908.7182 | 251908.7182 | 137845.3767 | 137845.3767 | 199035.9041 | 199035.9041 | 199035.9041 | 199035.9041 | 114367.0587 | 114367.0587 | 67757.7741 | 67757.7741 | 67757.7741 | 73758.2323 | 446415.5352 | 595014.706 | 595014.706 | 518557.1749 | 518557.1749 | 664371.5777 | 865189.8192 | 865189.8192 | 1158155.7281 | 762705.2474 | 762705.2474 | 924905.4135 | 663627.928 | 707124.1107 | 707124.1107 | 570186.1753 | 643504.6362 | 643504.6362 | 853773.3893 | 853773.3893 | 853773.3893 | 1012914.1593 | 1012914.1593 | 1072315.2212 | 1047041.3175 | 1098674.5868 | 1053524.6052 | 1206009.676 | 1096770.0282 | 1079265.8178 | 1079265.8178 | 1190826.3114 | 826318.5644 | 826318.5644 | 88459.1707 | 88459.1707 | 88459.1707 | 152493.0874
Tunel Largo | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 445749.6926 | 621665.8358 | 1230463.8272 | 1205617.5153 | 1665420.3985 | 1662826.7889 | 1510410.2355 | 1430287.7264 | 1354158.219 | 1349186.1344 | 1321718.5566 | 1455327.4271 | 1577653.4582 | 1622045.1942 | 1584199.6417 | 1460989.4038 | 1130593.0764 | 1040504.2599 | 1183988.0298 | 1029202.6329 | 1286232.4263 | 1184739.1462 | 1685078.0406 | 1604340.6056 | 1261701.9593 | 1378915.9437 | 1371249.4259 | 1467438.9007 | 1555516.0714 | 1473623.7094 | 1415547.4064 | 1415547.4064 | 1207769.1013 | 1022351.2297 | 1022351.2297 | 1220793.6788 | 1268502.749 | 1181029.5098 | 1148856.633 | 1148856.633 | 1048020.5007 | 1228279.3695 | 1192956.0837 | 1172612.6824 | 1313160.0802 | 1266176.7189 | 1248686.2535 | 1319612.1076
[45 empty] | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 421347.9907 | 597264.6339 | 1206066.6253 | 1181220.3134 | 1641024.1966 | 1638430.587 | 1486012.5336 | 1405889.5245 | 1329760.0171 | 1324787.9324 | 1297319.8547 | 1430929.2252 | 1553255.7563 | 1597647.4923 | 1559801.9397 | 1436590.7018 | 1106192.8744 | 1016104.558 | 1159589.3279 | 1004803.4309 | 1261834.2244 | 1160340.4442 | 1660680.8386 | 1579942.4037 | 1237301.7573 | 1354516.7417 | 1346851.2239 | 1443041.1988 | 1531119.3695 | 1449226.0075 | 1391149.2045 | 1391149.2045 | 1183369.3994 | 997951.0278 | 997951.0278 | 1196394.4768 | 1244104.047 | 1156629.8078 | 1124457.431 | 1124457.431 | 1023620.7987 | 1203880.6676 | 1168556.8818 | 1148213.4805 | 1288761.3782 | 1241777.5169 | 1224287.5515 | 1295213.9056
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25191 | 0.25191 | 0.13784 | 0.13784 | 0.19903 | 0.19903 | 0.19903 | 0.19903 | 0.11437 | 0.11437 | 0.067757 | 0.067757 | 0.067757 | 0.073758 | 0.44641 | 0.59501 | 0.59501 | 0.51856 | 0.51856 | 0.87416 | 1.075 | 1.075 | 1.3679 | 0.97249 | 1.2085 | 1.5466 | 1.8941 | 1.9127 | 2.3725 | 2.233 | 2.1539 | 2.0738 | 2.2079 | 2.203 | 2.1755 | 2.4682 | 2.5906 | 2.6944 | 2.6312 | 2.5597 | 2.1841 | 2.2465 | 2.2808 | 2.1085 | 2.3655 | 2.3756 | 2.5114 | 2.4307 | 1.3502 | 1.4674 | 1.4597 | 1.6199 | 1.5555 | 1.4736 | 1.4155 | 1.4155 | 1.2078 | 1.0224 | 1.0224 | 1.2208 | 1.2685 | 1.181 | 1.1489 | 1.1489 | 1.048 | 1.2283 | 1.193 | 1.1726 | 1.3132 | 1.2662 | 1.2487 | 1.3196
AGRUPACION DE SECUNDARIOS | GRUPO DE OBRAS
SECUNDARIOS ASOCIADOS AL TUNEL CORTO | A
B
SECUNDARIOS ASOCIADOS AL TUNEL LARGO | C
D
E
F
TOTAL=

## E
SECUNDARIO | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
|  | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5 | 11 | 11.5 | 12 | 12.5 | 13 | 13.5 | 14 | 14.5 | 15 | 15.5 | 16 | 16.5 | 17 | 17.5 | 18 | 18.5 | 19 | 19.5 | 20 | 20.5 | 21 | 21.5 | 22 | 22.5 | 23 | 23.5 | 24 | 24.5 | 25 | 25.5 | 26 | 26.5 | 27 | 27.5 | 28 | 28.5 | 29 | 29.5 | 30 | 30.5 | 31 | 31.5 | 32 | 32.5 | 33 | 33.5 | 34 | 34.5 | 35 | 35.5 | 36 | 36.5 | 37 | 37.5 | 38 | 38.5 | 39 | 39.5 | 40 | 40.5 | 41 | 41.5 | 42 | 42.5 | 43 | 43.5 | 44 | 44.5 | 45 | 45.5 | 46 | 46.5 | 47 | 47.5 | 48 | 48.5
Ramal Lugones | 6 | [44 empty] | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578
[46 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Casares | 3.5 | [56 empty] | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal F. Alcorta | 4.5 | [63 empty] | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521
[65 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Sur | 3.5 | [43 empty] | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Infanta Isabel | 2 | [46 empty] | 115462.5826 | 115462.5826 | 115462.5826 | 115462.5826
[48 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Norte | 0.5 | [46 empty] | 177502.3263
0.5
Ramal Libertador | 4 | [39 empty] | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707
[41 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sinclair | 1.5 | [44 empty] | 69347.9837 | 69347.9837 | 69347.9837
[46 empty] | 0.5 | 0.5 | 0.5
Ramal Arévalo | 2 | [24 empty] | 126822.0533 | 126822.0533 | 126822.0533 | 126822.0533
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Matienzo | 1 | [24 empty] | 58015.7901 | 58015.7901
[26 empty] | 0.5 | 0.5
Ramal Godoy Cruz | 2 | [28 empty] | 84668.3453 | 84668.3453 | 84668.3453 | 84668.3453
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Olleros | 3 | [28 empty] | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santa Fe | 1.5 | [34 empty] | 56734.4507 | 56734.4507 | 56734.4507
[36 empty] | 0.5 | 0.5 | 0.5
Ramal Fitz Roy | 0.5 | [37 empty] | 62734.9089
0.5
Ramal Bonpland | 1.5 | [38 empty] | 76457.031 | 76457.031 | 76457.031
[40 empty] | 0.5 | 0.5 | 0.5
Ramal Nicaragua | 1 | [24 empty] | 56046.5514 | 56046.5514
[26 empty] | 0.5 | 0.5
Ramal Costa Rica | 7 | [56 empty] | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Gurruchaga | 1 | [62 empty] | 45149.4816 | 45149.4816
[64 empty] | 0.5 | 0.5
Ramal Armenia | 1 | [65 empty] | 48214.397 | 48214.397
[67 empty] | 0.5 | 0.5
Ramal J. Alvarez | 0.5 | [69 empty] | 117835.6189
0.5
Ramal Lavalleja I | 1.5 | [69 empty] | 73082.7908 | 73082.7908 | 73082.7908
[71 empty] | 0.5 | 0.5 | 0.5
Ramal Cabrera | 1 | [49 empty] | 43239.6469 | 43239.6469
[51 empty] | 0.5 | 0.5
Ramal Niceto Vega Sur | 2 | [49 empty] | 72285.9116 | 72285.9116 | 72285.9116 | 72285.9116
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Niceto Vega Norte | 6 | [54 empty] | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742
[56 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Castillo | 0.5 | [65 empty] | 55621.4443
0.5
Ramal Acevedo | 1.5 | [51 empty] | 68757.9133 | 68757.9133 | 68757.9133
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Lavalleja II | 1 | [51 empty] | 64651.0238 | 64651.0238
[53 empty] | 0.5 | 0.5
Ramal Loyola | 6.5 | [59 empty] | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699
[61 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Velazco | 17 | [38 empty] | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808
[40 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal A. Gallardo | 0.5 | [61 empty] | 59400.5619
0.5
Ramal Lambaré | 1 | [65 empty] | 48647.7295 | 48647.7295
[67 empty] | 0.5 | 0.5
Ramal Estivao | 1 | [67 empty] | 79358.416 | 79358.416
[69 empty] | 0.5 | 0.5
Ramal Vera | 1 | [49 empty] | 46673.1076 | 46673.1076
[51 empty] | 0.5 | 0.5
Ramal Corrientes | 5 | [66 empty] | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707
[68 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Dorrego | 0.5 | [75 empty] | 64033.4167
0.5
Sumideros a Ramales Exist | 19 | [24 empty] | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Murillo | 2 | [68 empty] | 196896.1029 | 196896.1029 | 196896.1029 | 196896.1029
[70 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Muñecas Sur | 1.5 | [66 empty] | 68753.3919 | 68753.3919 | 68753.3919
[68 empty] | 0.5 | 0.5 | 0.5
Ramal Muñecas Norte | 1 | [68 empty] | 84870.5482 | 84870.5482
[70 empty] | 0.5 | 0.5
Ramal Darwin | 1 | [70 empty] | 34080.6876 | 34080.6876
[72 empty] | 0.5 | 0.5
Ramal M. Rosas | 4.5 | [52 empty] | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Caldas | 3 | [61 empty] | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223
[63 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santos Dumont | 1 | [67 empty] | 56626.5552 | 56626.5552
[69 empty] | 0.5 | 0.5
Ramal H. Pueyrredón | 8 | [70 empty] | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Tres Arroyos | 1.5 | [74 empty] | 56762.0448 | 56762.0448 | 56762.0448
[76 empty] | 0.5 | 0.5 | 0.5
Ramal Olaya | 1.5 | [77 empty] | 83417.4807 | 83417.4807 | 83417.4807
[79 empty] | 0.5 | 0.5 | 0.5
Ramal Rojas | 1 | [76 empty] | 39688.4802 | 39688.4802
[78 empty] | 0.5 | 0.5
Ramal Franklin | 1 | [83 empty] | 47703.7952 | 47703.7952
[85 empty] | 0.5 | 0.5
Ramal Arengreen | 5 | [86 empty] | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405
[88 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Aranguren | 1 | [94 empty] | 41661.2822 | 41661.2822
[96 empty] | 0.5 | 0.5
Ramal Cucha Cucha Sur | 2.5 | [50 empty] | 76191.728 | 76191.728 | 76191.728 | 76191.728 | 76191.728
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cucha Cucha Norte | 15.5 | [43 empty] | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Maturín | 1 | [61 empty] | 71493.528 | 71493.528
[63 empty] | 0.5 | 0.5
Ramal Constituyentes | 0.5 | [70 empty] | 38423.8726
0.5
Ramal Paysandú | 1 | [50 empty] | 46136.1796 | 46136.1796
[52 empty] | 0.5 | 0.5
Ramal San Martín | 5.5 | [74 empty] | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795
[76 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Camarones I | 5.5 | [85 empty] | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057
[87 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sánchez | 1 | [88 empty] | 35323.2858 | 35323.2858
[90 empty] | 0.5 | 0.5
Ramal A. Lamas | 1 | [91 empty] | 46983.3613 | 46983.3613
[93 empty] | 0.5 | 0.5
Ramal Seguí | 0.5 | [50 empty] | 77342.6992
0.5
Ramal Mendez de Andés | 5.5 | [49 empty] | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Calcena | 2 | [52 empty] | 59879.5762 | 59879.5762 | 59879.5762 | 59879.5762
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bogotá | 1.5 | [58 empty] | 76937.3008 | 76937.3008 | 76937.3008
[60 empty] | 0.5 | 0.5 | 0.5
Ramal Boyacá Sur | 1 | [52 empty] | 36412.3973 | 36412.3973
[54 empty] | 0.5 | 0.5
Ramal Boyacá Norte | 1.5 | [50 empty] | 50400.3835 | 50400.3835 | 50400.3835
[52 empty] | 0.5 | 0.5 | 0.5
Ramal Caracas | 18 | [60 empty] | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644
[62 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Biarritz | 1.5 | [75 empty] | 71933.6659 | 71933.6659 | 71933.6659
[77 empty] | 0.5 | 0.5 | 0.5
Ramal Carranza | 1 | [78 empty] | 46882.847 | 46882.847
[80 empty] | 0.5 | 0.5
Ramal Santo Tomé I | 0.5 | [84 empty] | 47709.0702
0.5
Ramal Empedrado | 1 | [89 empty] | 95763.2228 | 95763.2228
[91 empty] | 0.5 | 0.5
Ramal Zamudio | 2 | [92 empty] | 140547.3977 | 140547.3977 | 140547.3977 | 140547.3977
[94 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bufano | 1 | [55 empty] | 43875.9928 | 43875.9928
[57 empty] | 0.5 | 0.5
Ramal Bolivia Sur | 1.5 | [59 empty] | 111763.9143 | 111763.9143 | 111763.9143
[61 empty] | 0.5 | 0.5 | 0.5
Ramal Bolivia Norte | 0.5 | [61 empty] | 58219.7546
0.5
Ramal Terrada | 2 | [73 empty] | 63991.8159 | 63991.8159 | 63991.8159 | 63991.8159
[75 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Argerich Sur | 1 | [76 empty] | 48388.6905 | 48388.6905
[78 empty] | 0.5 | 0.5
Ramal Argerich Norte | 8.5 | [48 empty] | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Beláustegui | 1.5 | [51 empty] | 52496.3873 | 52496.3873 | 52496.3873
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Cesar Díaz | 1 | [57 empty] | 38903.9081 | 38903.9081
[59 empty] | 0.5 | 0.5
Ramal Camarones II | 1.5 | [60 empty] | 51716.7099 | 51716.7099 | 51716.7099
[62 empty] | 0.5 | 0.5 | 0.5
Ramal García I | 2 | [65 empty] | 67552.1337 | 67552.1337 | 67552.1337 | 67552.1337
[67 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Campana | 1 | [69 empty] | 42313.5624 | 42313.5624
[71 empty] | 0.5 | 0.5
Ramal Helguera | 1 | [70 empty] | 40587.2993 | 40587.2993
[72 empty] | 0.5 | 0.5
Ramal Galicia | 1.5 | [74 empty] | 44555.9821 | 44555.9821 | 44555.9821
[76 empty] | 0.5 | 0.5 | 0.5
Ramal E. González I | 1.5 | [78 empty] | 55051.6867 | 55051.6867 | 55051.6867
[80 empty] | 0.5 | 0.5 | 0.5
Ramal Vilardebó I | 7 | [50 empty] | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Vilardebó II | 1 | [62 empty] | 38173.1042 | 38173.1042
[64 empty] | 0.5 | 0.5
Ramal Bahía Blanca | 1 | [50 empty] | 61446.7283 | 61446.7283
[52 empty] | 0.5 | 0.5
Ramal E. Lamarca | 0.5 | [66 empty] | 74730.378
0.5
Ramal Chivilcoy | 0.5 | [67 empty] | 100452.7646
0.5
Ramal Sanabria | 1 | [68 empty] | 75715.9069 | 75715.9069
[70 empty] | 0.5 | 0.5
Ramal Segurola | 13 | [70 empty] | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal R. E. De San Martín | 1 | [73 empty] | 53222.1685 | 53222.1685
[75 empty] | 0.5 | 0.5
Ramal E. González II | 1 | [86 empty] | 40335.8049 | 40335.8049
[88 empty] | 0.5 | 0.5
Ramal Santo Tomé II | 1 | [94 empty] | 53780.3587 | 53780.3587
[96 empty] | 0.5 | 0.5
Ramal Goya | 0.5 | [69 empty] | 49125.2383
0.5
Ramal Carrasco | 2.5 | [75 empty] | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774
[77 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez II | 5.5 | [70 empty] | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez I | 3.5 | [81 empty] | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132
[83 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cervantes Sur | 1 | [52 empty] | 63507.7688 | 63507.7688
[54 empty] | 0.5 | 0.5
Ramal Cervantes Norte | 9 | [52 empty] | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Marcos Sastre | 1 | [70 empty] | 71074.5565 | 71074.5565
[72 empty] | 0.5 | 0.5
Ramal Calderón de la Barca | 1 | [50 empty] | 49190.8136 | 49190.8136
[52 empty] | 0.5 | 0.5
Ramal Milton | 1 | [53 empty] | 47806.7739 | 47806.7739
[55 empty] | 0.5 | 0.5
Ramal Virgilio | 1 | [56 empty] | 62504.4586 | 62504.4586
[58 empty] | 0.5 | 0.5
Ramal Victor Hugo | 1 | [59 empty] | 60748.8644 | 60748.8644
[61 empty] | 0.5 | 0.5
Ramal Camarones III | 1 | [62 empty] | 93965.0121 | 93965.0121
[64 empty] | 0.5 | 0.5
Ramal García II | 1 | [65 empty] | 53916.9164 | 53916.9164
[67 empty] | 0.5 | 0.5
Ramal Peralta | 1 | [50 empty] | 49831.2481 | 49831.2481
[52 empty] | 0.5 | 0.5
Ramal Alvarez Jonte | 2 | [52 empty] | 120654.8098 | 120654.8098 | 120654.8098 | 120654.8098
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Barragán | 1 | [56 empty] | 41900.42 | 41900.42
[58 empty] | 0.5 | 0.5
Ramal Cuzco Sur | 6.5 | [83 empty] | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539
[85 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Rivadavia I | 1 | [89 empty] | 84495.646 | 84495.646
[91 empty] | 0.5 | 0.5
Ramal Rivadavia II | 1.5 | [91 empty] | 112932.1063 | 112932.1063 | 112932.1063
[93 empty] | 0.5 | 0.5 | 0.5
Ramal Cuzco Norte | 0.5 | [95 empty] | 70925.8541
0.5
Sumideros a Ramales Exist | 24 | [48 empty] | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25191 | 0.25191 | 0.13785 | 0.13785 | 0.19904 | 0.19904 | 0.19904 | 0.19904 | 0.11437 | 0.11437 | 0.067758 | 0.067758 | 0.067758 | 0.073759 | 0.44642 | 0.59502 | 0.59502 | 0.51856 | 0.51856 | 0.87416 | 1.075 | 1.075 | 1.3679 | 0.9725 | 1.2085 | 1.5466 | 1.8941 | 1.9127 | 2.3726 | 2.233 | 2.1539 | 2.0738 | 2.2079 | 2.203 | 2.1755 | 2.4682 | 2.5906 | 2.6944 | 2.6312 | 2.5597 | 2.1841 | 2.2465 | 2.2808 | 2.1085 | 2.3655 | 2.3756 | 2.5114 | 2.4307 | 1.3502 | 1.4674 | 1.4597 | 1.6199 | 1.5555 | 1.4736 | 1.4156 | 1.4156 | 1.2078 | 1.0224 | 1.0224 | 1.2208 | 1.2685 | 1.181 | 1.1489 | 1.1489 | 1.048 | 1.2283 | 1.193 | 1.1726 | 1.3132 | 1.2662 | 1.2487 | 1.3196
TUNEL | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
Tunel Corto | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251907.2182 | 251907.2182 | 137844.8767 | 137844.8767 | 199034.9041 | 199034.9041 | 199034.9041 | 199034.9041 | 114366.5587 | 114366.5587 | 67757.2741 | 67757.2741 | 67757.2741 | 73757.7323 | 446414.5352 | 595013.206 | 595013.206 | 518556.1749 | 518556.1749 | 664370.0777 | 865187.3192 | 865187.3192 | 1158152.2281 | 762703.2474 | 762703.2474 | 924901.9135 | 663625.428 | 707121.6107 | 707121.6107 | 570184.6753 | 643503.1362 | 643503.1362 | 853771.3893 | 853771.3893 | 853771.3893 | 1012911.6593 | 1012911.6593 | 1072312.2212 | 1047038.3175 | 1098671.5868 | 1053522.1052 | 1206005.676 | 1096766.5282 | 1079262.8178 | 1079262.8178 | 1190822.8114 | 826316.0644 | 826316.0644 | 88458.6707 | 88458.6707 | 88458.6707 | 152492.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 251908.7182 | 251908.7182 | 137845.3767 | 137845.3767 | 199035.9041 | 199035.9041 | 199035.9041 | 199035.9041 | 114367.0587 | 114367.0587 | 67757.7741 | 67757.7741 | 67757.7741 | 73758.2323 | 446415.5352 | 595014.706 | 595014.706 | 518557.1749 | 518557.1749 | 664371.5777 | 865189.8192 | 865189.8192 | 1158155.7281 | 762705.2474 | 762705.2474 | 924905.4135 | 663627.928 | 707124.1107 | 707124.1107 | 570186.1753 | 643504.6362 | 643504.6362 | 853773.3893 | 853773.3893 | 853773.3893 | 1012914.1593 | 1012914.1593 | 1072315.2212 | 1047041.3175 | 1098674.5868 | 1053524.6052 | 1206009.676 | 1096770.0282 | 1079265.8178 | 1079265.8178 | 1190826.3114 | 826318.5644 | 826318.5644 | 88459.1707 | 88459.1707 | 88459.1707 | 152493.0874
Tunel Largo | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 445749.6926 | 621665.8358 | 1230463.8272 | 1205617.5153 | 1665420.3985 | 1662826.7889 | 1510410.2355 | 1430287.7264 | 1354158.219 | 1349186.1344 | 1321718.5566 | 1455327.4271 | 1577653.4582 | 1622045.1942 | 1584199.6417 | 1460989.4038 | 1130593.0764 | 1040504.2599 | 1183988.0298 | 1029202.6329 | 1286232.4263 | 1184739.1462 | 1685078.0406 | 1604340.6056 | 1261701.9593 | 1378915.9437 | 1371249.4259 | 1467438.9007 | 1555516.0714 | 1473623.7094 | 1415547.4064 | 1415547.4064 | 1207769.1013 | 1022351.2297 | 1022351.2297 | 1220793.6788 | 1268502.749 | 1181029.5098 | 1148856.633 | 1148856.633 | 1048020.5007 | 1228279.3695 | 1192956.0837 | 1172612.6824 | 1313160.0802 | 1266176.7189 | 1248686.2535 | 1319612.1076
[45 empty] | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 421347.9907 | 597264.6339 | 1206066.6253 | 1181220.3134 | 1641024.1966 | 1638430.587 | 1486012.5336 | 1405889.5245 | 1329760.0171 | 1324787.9324 | 1297319.8547 | 1430929.2252 | 1553255.7563 | 1597647.4923 | 1559801.9397 | 1436590.7018 | 1106192.8744 | 1016104.558 | 1159589.3279 | 1004803.4309 | 1261834.2244 | 1160340.4442 | 1660680.8386 | 1579942.4037 | 1237301.7573 | 1354516.7417 | 1346851.2239 | 1443041.1988 | 1531119.3695 | 1449226.0075 | 1391149.2045 | 1391149.2045 | 1183369.3994 | 997951.0278 | 997951.0278 | 1196394.4768 | 1244104.047 | 1156629.8078 | 1124457.431 | 1124457.431 | 1023620.7987 | 1203880.6676 | 1168556.8818 | 1148213.4805 | 1288761.3782 | 1241777.5169 | 1224287.5515 | 1295213.9056
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25191 | 0.25191 | 0.13784 | 0.13784 | 0.19903 | 0.19903 | 0.19903 | 0.19903 | 0.11437 | 0.11437 | 0.067757 | 0.067757 | 0.067757 | 0.073758 | 0.44641 | 0.59501 | 0.59501 | 0.51856 | 0.51856 | 0.87416 | 1.075 | 1.075 | 1.3679 | 0.97249 | 1.2085 | 1.5466 | 1.8941 | 1.9127 | 2.3725 | 2.233 | 2.1539 | 2.0738 | 2.2079 | 2.203 | 2.1755 | 2.4682 | 2.5906 | 2.6944 | 2.6312 | 2.5597 | 2.1841 | 2.2465 | 2.2808 | 2.1085 | 2.3655 | 2.3756 | 2.5114 | 2.4307 | 1.3502 | 1.4674 | 1.4597 | 1.6199 | 1.5555 | 1.4736 | 1.4155 | 1.4155 | 1.2078 | 1.0224 | 1.0224 | 1.2208 | 1.2685 | 1.181 | 1.1489 | 1.1489 | 1.048 | 1.2283 | 1.193 | 1.1726 | 1.3132 | 1.2662 | 1.2487 | 1.3196
AGRUPACION DE SECUNDARIOS | GRUPO DE OBRAS
SECUNDARIOS ASOCIADOS AL TUNEL CORTO | A
B
SECUNDARIOS ASOCIADOS AL TUNEL LARGO | C
D
E
F
TOTAL=

## F
SECUNDARIO | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
|  | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5 | 11 | 11.5 | 12 | 12.5 | 13 | 13.5 | 14 | 14.5 | 15 | 15.5 | 16 | 16.5 | 17 | 17.5 | 18 | 18.5 | 19 | 19.5 | 20 | 20.5 | 21 | 21.5 | 22 | 22.5 | 23 | 23.5 | 24 | 24.5 | 25 | 25.5 | 26 | 26.5 | 27 | 27.5 | 28 | 28.5 | 29 | 29.5 | 30 | 30.5 | 31 | 31.5 | 32 | 32.5 | 33 | 33.5 | 34 | 34.5 | 35 | 35.5 | 36 | 36.5 | 37 | 37.5 | 38 | 38.5 | 39 | 39.5 | 40 | 40.5 | 41 | 41.5 | 42 | 42.5 | 43 | 43.5 | 44 | 44.5 | 45 | 45.5 | 46 | 46.5 | 47 | 47.5 | 48 | 48.5
Ramal Lugones | 6 | [44 empty] | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578 | 131469.2578
[46 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Casares | 3.5 | [56 empty] | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828 | 95066.3828
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal F. Alcorta | 4.5 | [63 empty] | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521 | 146699.6521
[65 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Sur | 3.5 | [43 empty] | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028 | 145813.9028
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Infanta Isabel | 2 | [46 empty] | 115462.5826 | 115462.5826 | 115462.5826 | 115462.5826
[48 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Freyre Norte | 0.5 | [46 empty] | 177502.3263
0.5
Ramal Libertador | 4 | [39 empty] | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707 | 148598.6707
[41 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sinclair | 1.5 | [44 empty] | 69347.9837 | 69347.9837 | 69347.9837
[46 empty] | 0.5 | 0.5 | 0.5
Ramal Arévalo | 2 | [24 empty] | 126822.0533 | 126822.0533 | 126822.0533 | 126822.0533
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Matienzo | 1 | [24 empty] | 58015.7901 | 58015.7901
[26 empty] | 0.5 | 0.5
Ramal Godoy Cruz | 2 | [28 empty] | 84668.3453 | 84668.3453 | 84668.3453 | 84668.3453
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Olleros | 3 | [28 empty] | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354 | 103343.7354
[30 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santa Fe | 1.5 | [34 empty] | 56734.4507 | 56734.4507 | 56734.4507
[36 empty] | 0.5 | 0.5 | 0.5
Ramal Fitz Roy | 0.5 | [37 empty] | 62734.9089
0.5
Ramal Bonpland | 1.5 | [38 empty] | 76457.031 | 76457.031 | 76457.031
[40 empty] | 0.5 | 0.5 | 0.5
Ramal Nicaragua | 1 | [24 empty] | 56046.5514 | 56046.5514
[26 empty] | 0.5 | 0.5
Ramal Costa Rica | 7 | [56 empty] | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282 | 246671.1282
[58 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Gurruchaga | 1 | [62 empty] | 45149.4816 | 45149.4816
[64 empty] | 0.5 | 0.5
Ramal Armenia | 1 | [65 empty] | 48214.397 | 48214.397
[67 empty] | 0.5 | 0.5
Ramal J. Alvarez | 0.5 | [69 empty] | 117835.6189
0.5
Ramal Lavalleja I | 1.5 | [69 empty] | 73082.7908 | 73082.7908 | 73082.7908
[71 empty] | 0.5 | 0.5 | 0.5
Ramal Cabrera | 1 | [49 empty] | 43239.6469 | 43239.6469
[51 empty] | 0.5 | 0.5
Ramal Niceto Vega Sur | 2 | [49 empty] | 72285.9116 | 72285.9116 | 72285.9116 | 72285.9116
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Niceto Vega Norte | 6 | [54 empty] | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742 | 142076.3742
[56 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Castillo | 0.5 | [65 empty] | 55621.4443
0.5
Ramal Acevedo | 1.5 | [51 empty] | 68757.9133 | 68757.9133 | 68757.9133
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Lavalleja II | 1 | [51 empty] | 64651.0238 | 64651.0238
[53 empty] | 0.5 | 0.5
Ramal Loyola | 6.5 | [59 empty] | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699 | 159140.2699
[61 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Velazco | 17 | [38 empty] | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808 | 358934.6808
[40 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal A. Gallardo | 0.5 | [61 empty] | 59400.5619
0.5
Ramal Lambaré | 1 | [65 empty] | 48647.7295 | 48647.7295
[67 empty] | 0.5 | 0.5
Ramal Estivao | 1 | [67 empty] | 79358.416 | 79358.416
[69 empty] | 0.5 | 0.5
Ramal Vera | 1 | [49 empty] | 46673.1076 | 46673.1076
[51 empty] | 0.5 | 0.5
Ramal Corrientes | 5 | [66 empty] | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707 | 88458.6707
[68 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Dorrego | 0.5 | [75 empty] | 64033.4167
0.5
Sumideros a Ramales Exist | 19 | [24 empty] | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234 | 11022.8234
[26 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Murillo | 2 | [68 empty] | 196896.1029 | 196896.1029 | 196896.1029 | 196896.1029
[70 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Muñecas Sur | 1.5 | [66 empty] | 68753.3919 | 68753.3919 | 68753.3919
[68 empty] | 0.5 | 0.5 | 0.5
Ramal Muñecas Norte | 1 | [68 empty] | 84870.5482 | 84870.5482
[70 empty] | 0.5 | 0.5
Ramal Darwin | 1 | [70 empty] | 34080.6876 | 34080.6876
[72 empty] | 0.5 | 0.5
Ramal M. Rosas | 4.5 | [52 empty] | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037 | 130852.8037
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Caldas | 3 | [61 empty] | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223 | 183217.4223
[63 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Santos Dumont | 1 | [67 empty] | 56626.5552 | 56626.5552
[69 empty] | 0.5 | 0.5
Ramal H. Pueyrredón | 8 | [70 empty] | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221 | 251281.8221
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Tres Arroyos | 1.5 | [74 empty] | 56762.0448 | 56762.0448 | 56762.0448
[76 empty] | 0.5 | 0.5 | 0.5
Ramal Olaya | 1.5 | [77 empty] | 83417.4807 | 83417.4807 | 83417.4807
[79 empty] | 0.5 | 0.5 | 0.5
Ramal Rojas | 1 | [76 empty] | 39688.4802 | 39688.4802
[78 empty] | 0.5 | 0.5
Ramal Franklin | 1 | [83 empty] | 47703.7952 | 47703.7952
[85 empty] | 0.5 | 0.5
Ramal Arengreen | 5 | [86 empty] | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405 | 178773.1405
[88 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Aranguren | 1 | [94 empty] | 41661.2822 | 41661.2822
[96 empty] | 0.5 | 0.5
Ramal Cucha Cucha Sur | 2.5 | [50 empty] | 76191.728 | 76191.728 | 76191.728 | 76191.728 | 76191.728
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cucha Cucha Norte | 15.5 | [43 empty] | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241
[45 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Maturín | 1 | [61 empty] | 71493.528 | 71493.528
[63 empty] | 0.5 | 0.5
Ramal Constituyentes | 0.5 | [70 empty] | 38423.8726
0.5
Ramal Paysandú | 1 | [50 empty] | 46136.1796 | 46136.1796
[52 empty] | 0.5 | 0.5
Ramal San Martín | 5.5 | [74 empty] | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795 | 100804.5795
[76 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Camarones I | 5.5 | [85 empty] | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057 | 108744.2057
[87 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Sánchez | 1 | [88 empty] | 35323.2858 | 35323.2858
[90 empty] | 0.5 | 0.5
Ramal A. Lamas | 1 | [91 empty] | 46983.3613 | 46983.3613
[93 empty] | 0.5 | 0.5
Ramal Seguí | 0.5 | [50 empty] | 77342.6992
0.5
Ramal Mendez de Andés | 5.5 | [49 empty] | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432 | 175916.1432
[51 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Calcena | 2 | [52 empty] | 59879.5762 | 59879.5762 | 59879.5762 | 59879.5762
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bogotá | 1.5 | [58 empty] | 76937.3008 | 76937.3008 | 76937.3008
[60 empty] | 0.5 | 0.5 | 0.5
Ramal Boyacá Sur | 1 | [52 empty] | 36412.3973 | 36412.3973
[54 empty] | 0.5 | 0.5
Ramal Boyacá Norte | 1.5 | [50 empty] | 50400.3835 | 50400.3835 | 50400.3835
[52 empty] | 0.5 | 0.5 | 0.5
Ramal Caracas | 18 | [60 empty] | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644 | 246525.4644
[62 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Biarritz | 1.5 | [75 empty] | 71933.6659 | 71933.6659 | 71933.6659
[77 empty] | 0.5 | 0.5 | 0.5
Ramal Carranza | 1 | [78 empty] | 46882.847 | 46882.847
[80 empty] | 0.5 | 0.5
Ramal Santo Tomé I | 0.5 | [84 empty] | 47709.0702
0.5
Ramal Empedrado | 1 | [89 empty] | 95763.2228 | 95763.2228
[91 empty] | 0.5 | 0.5
Ramal Zamudio | 2 | [92 empty] | 140547.3977 | 140547.3977 | 140547.3977 | 140547.3977
[94 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bufano | 1 | [55 empty] | 43875.9928 | 43875.9928
[57 empty] | 0.5 | 0.5
Ramal Bolivia Sur | 1.5 | [59 empty] | 111763.9143 | 111763.9143 | 111763.9143
[61 empty] | 0.5 | 0.5 | 0.5
Ramal Bolivia Norte | 0.5 | [61 empty] | 58219.7546
0.5
Ramal Terrada | 2 | [73 empty] | 63991.8159 | 63991.8159 | 63991.8159 | 63991.8159
[75 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Argerich Sur | 1 | [76 empty] | 48388.6905 | 48388.6905
[78 empty] | 0.5 | 0.5
Ramal Argerich Norte | 8.5 | [48 empty] | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666 | 211557.8666
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Beláustegui | 1.5 | [51 empty] | 52496.3873 | 52496.3873 | 52496.3873
[53 empty] | 0.5 | 0.5 | 0.5
Ramal Cesar Díaz | 1 | [57 empty] | 38903.9081 | 38903.9081
[59 empty] | 0.5 | 0.5
Ramal Camarones II | 1.5 | [60 empty] | 51716.7099 | 51716.7099 | 51716.7099
[62 empty] | 0.5 | 0.5 | 0.5
Ramal García I | 2 | [65 empty] | 67552.1337 | 67552.1337 | 67552.1337 | 67552.1337
[67 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Campana | 1 | [69 empty] | 42313.5624 | 42313.5624
[71 empty] | 0.5 | 0.5
Ramal Helguera | 1 | [70 empty] | 40587.2993 | 40587.2993
[72 empty] | 0.5 | 0.5
Ramal Galicia | 1.5 | [74 empty] | 44555.9821 | 44555.9821 | 44555.9821
[76 empty] | 0.5 | 0.5 | 0.5
Ramal E. González I | 1.5 | [78 empty] | 55051.6867 | 55051.6867 | 55051.6867
[80 empty] | 0.5 | 0.5 | 0.5
Ramal Vilardebó I | 7 | [50 empty] | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111 | 198258.2111
[52 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Vilardebó II | 1 | [62 empty] | 38173.1042 | 38173.1042
[64 empty] | 0.5 | 0.5
Ramal Bahía Blanca | 1 | [50 empty] | 61446.7283 | 61446.7283
[52 empty] | 0.5 | 0.5
Ramal E. Lamarca | 0.5 | [66 empty] | 74730.378
0.5
Ramal Chivilcoy | 0.5 | [67 empty] | 100452.7646
0.5
Ramal Sanabria | 1 | [68 empty] | 75715.9069 | 75715.9069
[70 empty] | 0.5 | 0.5
Ramal Segurola | 13 | [70 empty] | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485 | 303513.0485
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal R. E. De San Martín | 1 | [73 empty] | 53222.1685 | 53222.1685
[75 empty] | 0.5 | 0.5
Ramal E. González II | 1 | [86 empty] | 40335.8049 | 40335.8049
[88 empty] | 0.5 | 0.5
Ramal Santo Tomé II | 1 | [94 empty] | 53780.3587 | 53780.3587
[96 empty] | 0.5 | 0.5
Ramal Goya | 0.5 | [69 empty] | 49125.2383
0.5
Ramal Carrasco | 2.5 | [75 empty] | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774 | 77477.9774
[77 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez II | 5.5 | [70 empty] | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982 | 226189.7982
[72 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Bermúdez I | 3.5 | [81 empty] | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132 | 95823.6132
[83 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Cervantes Sur | 1 | [52 empty] | 63507.7688 | 63507.7688
[54 empty] | 0.5 | 0.5
Ramal Cervantes Norte | 9 | [52 empty] | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971 | 255100.4971
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Marcos Sastre | 1 | [70 empty] | 71074.5565 | 71074.5565
[72 empty] | 0.5 | 0.5
Ramal Calderón de la Barca | 1 | [50 empty] | 49190.8136 | 49190.8136
[52 empty] | 0.5 | 0.5
Ramal Milton | 1 | [53 empty] | 47806.7739 | 47806.7739
[55 empty] | 0.5 | 0.5
Ramal Virgilio | 1 | [56 empty] | 62504.4586 | 62504.4586
[58 empty] | 0.5 | 0.5
Ramal Victor Hugo | 1 | [59 empty] | 60748.8644 | 60748.8644
[61 empty] | 0.5 | 0.5
Ramal Camarones III | 1 | [62 empty] | 93965.0121 | 93965.0121
[64 empty] | 0.5 | 0.5
Ramal García II | 1 | [65 empty] | 53916.9164 | 53916.9164
[67 empty] | 0.5 | 0.5
Ramal Peralta | 1 | [50 empty] | 49831.2481 | 49831.2481
[52 empty] | 0.5 | 0.5
Ramal Alvarez Jonte | 2 | [52 empty] | 120654.8098 | 120654.8098 | 120654.8098 | 120654.8098
[54 empty] | 0.5 | 0.5 | 0.5 | 0.5
Ramal Barragán | 1 | [56 empty] | 41900.42 | 41900.42
[58 empty] | 0.5 | 0.5
Ramal Cuzco Sur | 6.5 | [83 empty] | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539 | 150738.6539
[85 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Ramal Rivadavia I | 1 | [89 empty] | 84495.646 | 84495.646
[91 empty] | 0.5 | 0.5
Ramal Rivadavia II | 1.5 | [91 empty] | 112932.1063 | 112932.1063 | 112932.1063
[93 empty] | 0.5 | 0.5 | 0.5
Ramal Cuzco Norte | 0.5 | [95 empty] | 70925.8541
0.5
Sumideros a Ramales Exist | 24 | [48 empty] | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702 | 24402.702
[50 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25191 | 0.25191 | 0.13785 | 0.13785 | 0.19904 | 0.19904 | 0.19904 | 0.19904 | 0.11437 | 0.11437 | 0.067758 | 0.067758 | 0.067758 | 0.073759 | 0.44642 | 0.59502 | 0.59502 | 0.51856 | 0.51856 | 0.87416 | 1.075 | 1.075 | 1.3679 | 0.9725 | 1.2085 | 1.5466 | 1.8941 | 1.9127 | 2.3726 | 2.233 | 2.1539 | 2.0738 | 2.2079 | 2.203 | 2.1755 | 2.4682 | 2.5906 | 2.6944 | 2.6312 | 2.5597 | 2.1841 | 2.2465 | 2.2808 | 2.1085 | 2.3655 | 2.3756 | 2.5114 | 2.4307 | 1.3502 | 1.4674 | 1.4597 | 1.6199 | 1.5555 | 1.4736 | 1.4156 | 1.4156 | 1.2078 | 1.0224 | 1.0224 | 1.2208 | 1.2685 | 1.181 | 1.1489 | 1.1489 | 1.048 | 1.2283 | 1.193 | 1.1726 | 1.3132 | 1.2662 | 1.2487 | 1.3196
TUNEL | DURACIÓN | AÑO 1 | [23 empty] | AÑO 2 | [23 empty] | AÑO 3 | [23 empty] | AÑO 4
| (Meses) | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48
Tunel Corto | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251907.2182 | 251907.2182 | 137844.8767 | 137844.8767 | 199034.9041 | 199034.9041 | 199034.9041 | 199034.9041 | 114366.5587 | 114366.5587 | 67757.2741 | 67757.2741 | 67757.2741 | 73757.7323 | 446414.5352 | 595013.206 | 595013.206 | 518556.1749 | 518556.1749 | 664370.0777 | 865187.3192 | 865187.3192 | 1158152.2281 | 762703.2474 | 762703.2474 | 924901.9135 | 663625.428 | 707121.6107 | 707121.6107 | 570184.6753 | 643503.1362 | 643503.1362 | 853771.3893 | 853771.3893 | 853771.3893 | 1012911.6593 | 1012911.6593 | 1072312.2212 | 1047038.3175 | 1098671.5868 | 1053522.1052 | 1206005.676 | 1096766.5282 | 1079262.8178 | 1079262.8178 | 1190822.8114 | 826316.0644 | 826316.0644 | 88458.6707 | 88458.6707 | 88458.6707 | 152492.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 251908.7182 | 251908.7182 | 137845.3767 | 137845.3767 | 199035.9041 | 199035.9041 | 199035.9041 | 199035.9041 | 114367.0587 | 114367.0587 | 67757.7741 | 67757.7741 | 67757.7741 | 73758.2323 | 446415.5352 | 595014.706 | 595014.706 | 518557.1749 | 518557.1749 | 664371.5777 | 865189.8192 | 865189.8192 | 1158155.7281 | 762705.2474 | 762705.2474 | 924905.4135 | 663627.928 | 707124.1107 | 707124.1107 | 570186.1753 | 643504.6362 | 643504.6362 | 853773.3893 | 853773.3893 | 853773.3893 | 1012914.1593 | 1012914.1593 | 1072315.2212 | 1047041.3175 | 1098674.5868 | 1053524.6052 | 1206009.676 | 1096770.0282 | 1079265.8178 | 1079265.8178 | 1190826.3114 | 826318.5644 | 826318.5644 | 88459.1707 | 88459.1707 | 88459.1707 | 152493.0874
Tunel Largo | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 209789.1241 | 445749.6926 | 621665.8358 | 1230463.8272 | 1205617.5153 | 1665420.3985 | 1662826.7889 | 1510410.2355 | 1430287.7264 | 1354158.219 | 1349186.1344 | 1321718.5566 | 1455327.4271 | 1577653.4582 | 1622045.1942 | 1584199.6417 | 1460989.4038 | 1130593.0764 | 1040504.2599 | 1183988.0298 | 1029202.6329 | 1286232.4263 | 1184739.1462 | 1685078.0406 | 1604340.6056 | 1261701.9593 | 1378915.9437 | 1371249.4259 | 1467438.9007 | 1555516.0714 | 1473623.7094 | 1415547.4064 | 1415547.4064 | 1207769.1013 | 1022351.2297 | 1022351.2297 | 1220793.6788 | 1268502.749 | 1181029.5098 | 1148856.633 | 1148856.633 | 1048020.5007 | 1228279.3695 | 1192956.0837 | 1172612.6824 | 1313160.0802 | 1266176.7189 | 1248686.2535 | 1319612.1076
[45 empty] | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 209789.6241 | 421347.9907 | 597264.6339 | 1206066.6253 | 1181220.3134 | 1641024.1966 | 1638430.587 | 1486012.5336 | 1405889.5245 | 1329760.0171 | 1324787.9324 | 1297319.8547 | 1430929.2252 | 1553255.7563 | 1597647.4923 | 1559801.9397 | 1436590.7018 | 1106192.8744 | 1016104.558 | 1159589.3279 | 1004803.4309 | 1261834.2244 | 1160340.4442 | 1660680.8386 | 1579942.4037 | 1237301.7573 | 1354516.7417 | 1346851.2239 | 1443041.1988 | 1531119.3695 | 1449226.0075 | 1391149.2045 | 1391149.2045 | 1183369.3994 | 997951.0278 | 997951.0278 | 1196394.4768 | 1244104.047 | 1156629.8078 | 1124457.431 | 1124457.431 | 1023620.7987 | 1203880.6676 | 1168556.8818 | 1148213.4805 | 1288761.3782 | 1241777.5169 | 1224287.5515 | 1295213.9056
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25191 | 0.25191 | 0.13784 | 0.13784 | 0.19903 | 0.19903 | 0.19903 | 0.19903 | 0.11437 | 0.11437 | 0.067757 | 0.067757 | 0.067757 | 0.073758 | 0.44641 | 0.59501 | 0.59501 | 0.51856 | 0.51856 | 0.87416 | 1.075 | 1.075 | 1.3679 | 0.97249 | 1.2085 | 1.5466 | 1.8941 | 1.9127 | 2.3725 | 2.233 | 2.1539 | 2.0738 | 2.2079 | 2.203 | 2.1755 | 2.4682 | 2.5906 | 2.6944 | 2.6312 | 2.5597 | 2.1841 | 2.2465 | 2.2808 | 2.1085 | 2.3655 | 2.3756 | 2.5114 | 2.4307 | 1.3502 | 1.4674 | 1.4597 | 1.6199 | 1.5555 | 1.4736 | 1.4155 | 1.4155 | 1.2078 | 1.0224 | 1.0224 | 1.2208 | 1.2685 | 1.181 | 1.1489 | 1.1489 | 1.048 | 1.2283 | 1.193 | 1.1726 | 1.3132 | 1.2662 | 1.2487 | 1.3196
AGRUPACION DE SECUNDARIOS | GRUPO DE OBRAS
SECUNDARIOS ASOCIADOS AL TUNEL CORTO | A
B
SECUNDARIOS ASOCIADOS AL TUNEL LARGO | C
D
E
F
TOTAL=